## Overview & Disclaimer
DISCLAIMER | The content contained in this template is provided for general information purposes only. The provision of this template, and the information contained in the template itself, does not constitute legal advice or opinions of any kind. Your use of these documents is at your own risk, and you should not use this template without first seeking legal and other professional advice.
The Master Diligence Request List is intended to provide an inclusive and wide-ranging list of initial due diligence requests that can be used for any target in any type of transaction. As used in this template, "Target" means the target company and all of its direct and indirect subsidiaries and affiliates.
The requests contained in this template are intended to be initial requests, drafted in order to solicit general information that will provide the buyer with a broad overview of the Target and its business and operations. Information provided by the Target in response to these requests will likely trigger additional questions that focus on specific aspects of the Target's business and issues identified during the due diligence process.
This template is not, and does not purport to be, complete. Likewise, some requests included herein may not be appropriate for your specific transaction. Before utilizing this template, it should be evaluated with the help of your legal and other professional advisors to ensure that your diligence requests are tailored to the specific circumstances of your transaction.

## Finance Integration
Title | Description | Category | Priority | Status
Identify Major Finance Processes in Scope for the Transaction per the Finance Charter |  | Define Day 1 Target Operating Model, Team Staffing Approach, and Program Budget | Low | Open
Identify Subprocesses for each Major Finance Process |  | Define Day 1 Target Operating Model, Team Staffing Approach, and Program Budget | Low | Open
Define Day 1 Finance Organization Design, Roles, & Responsibilities |  | Define Day 1 Target Operating Model, Team Staffing Approach, and Program Budget | Low | Open
Define Day 1 Finance Processes and Policies |  | Define Day 1 Target Operating Model, Team Staffing Approach, and Program Budget | Low | Open
Define Day 1 Finance Facilities/Locations |  | Define Day 1 Target Operating Model, Team Staffing Approach, and Program Budget | Low | Open
Define Day 1 Finance Systems |  | Define Day 1 Target Operating Model, Team Staffing Approach, and Program Budget | Low | Open
Conduct Cross-Functional Validation to Ensure Day 1 Target Operating Model Assumptions are Consistent and Viable |  | Define Day 1 Target Operating Model, Team Staffing Approach, and Program Budget | Low | Open
Based on Target Operating Model, Define Integration Program Exit Activities/Milestones |  | Define Day 1 Target Operating Model, Team Staffing Approach, and Program Budget | Low | Open
Review Overall Finance Internal Projects Roadmap, Postpone All Non-Critical Roadmap Projects to Allow Acquisition Focus |  | Define Day 1 Target Operating Model, Team Staffing Approach, and Program Budget | Low | Open
Alongside Integration Leadership, Determine Finance Program Staffing Model Considering all TOM Requirements, Scope, and Timing Needs |  | Define Day 1 Target Operating Model, Team Staffing Approach, and Program Budget | Low | Open
Compile Overall Finance Program Budgeting in Accordance with Guidelines Established by Integration Leadership, Adding Contingency Commensurate with Integration Uncertainty, i.e. 10-15% Initially, Reducing with Iteration When Possible |  | Define Day 1 Target Operating Model, Team Staffing Approach, and Program Budget | Low | Open
Draft Any New Job Descriptions and Get Approval from HR |  | Address Finance Organization Design, Processes, and Policies | Low | Open
Ensure All Finance Onboarding Requirements Addressed by Program-wide Onboarding Plan, Fill Gaps if Needed |  | Address Finance Organization Design, Processes, and Policies | Low | Open
Document New/Altered Finance Processes, Including Controls |  | Address Finance Organization Design, Processes, and Policies | Low | Open
Document New/Altered Finance Policies |  | Address Finance Organization Design, Processes, and Policies | Low | Open
Identify and Address Finance Training Requirements for Day 1 |  | Address Finance Organization Design, Processes, and Policies | Low | Open
Address Departmental Performance Measurement and Incentives |  | Address Finance Organization Design, Processes, and Policies | Low | Open
Ensure Facilities Plan Aligns with Finance Organization Design Including Seating, Conference Rooms, and Auditor Facilities |  | Address Finance Facilities | Low | Open
Ensure Facilities Plan Accommodates Finance Network and Telephony Requirements, Including Access to All Finance Systems Day 1 |  | Address Finance Facilities | Low | Open
Address Finance Systems |  | Address Finance Systems | Low | Open
Ensure All Finance Systems are Included on IT Systems Inventory |  | Address Finance Systems | Low | Open
Define Desired Functionality for New/Altered Systems |  | Address Finance Systems | Low | Open
Define New Finance Data Structures: Chart of Accounts, Legal Entities, Profit Centers, Cost Centers |  | Address Finance Systems | Low | Open
Define New/Altered Requirements for Complicance:Tax, Statutory/Regulatory Reporting, Customs, GAAP/IFRS, Intercompany, Historical |  | Address Finance Systems | Low | Open
Conduct Data Mapping into New/Altered Data Structure |  | Address Finance Systems | Low | Open
Refine Finance RICEFW Inventory with IT (Reports, Interfaces, Conversions, Extensions, Forms, and Workflows) |  | Address Finance Systems | Low | Open
Assist IT with User Testing of Finance Systems for Day 1 Deployment |  | Address Finance Systems | Low | Open
Ensure Adequate Finance Data Retention/Archiving for Historical Reporting and Compliance |  | Address Finance Systems | Low | Open
Establish Capital Stack for the Transaction |  | Complete Deal Accounting Activities | Low | Open
Establish and Fund Escrow Arrangements |  | Complete Deal Accounting Activities | Low | Open
Prepare Purchase Price Accounting |  | Complete Deal Accounting Activities | Low | Open
Schedule and Execute Asset Inventories |  | Complete Deal Accounting Activities | Low | Open
Schedule and Execute Inventory Physical Counts |  | Complete Deal Accounting Activities | Low | Open
Prepare Short Period Reports and Tax Returns |  | Complete Deal Accounting Activities | Low | Open
Determine Accounting Principles for the Combined Entity |  | Reporting, Budgeting, Assets | Low | Open
Evaluate Deferrals. Contingency Accruals, Etc. And Adjust for Combined Entity as Needed |  | Reporting, Budgeting, Assets | Low | Open
Evaluate Historical Budgeting and Forecasting Materials from Diligence |  | Reporting, Budgeting, Assets | Low | Open
Evaluate and Consolidate Capital Spending Plans/Commitments |  | Reporting, Budgeting, Assets | Low | Open
Align Capitalization Policies, Including WIP, Capitalized Labor, Etc. |  | Reporting, Budgeting, Assets | Low | Open
Setup Fixed Assets in Asset Management System at PPA Valuations |  | Reporting, Budgeting, Assets | Low | Open
Establish Opening Balance Sheet |  | Reporting, Budgeting, Assets | Low | Open
Rollout New Chart of Accounts, Profit Centers, and Cost Centers |  | Reporting, Budgeting, Assets | Low | Open
Establish New Budgeting Policies and Procedures |  | Reporting, Budgeting, Assets | Low | Open
Prepare Initial Combined Budgets and Forecasts |  | Reporting, Budgeting, Assets | Low | Open
Rollout New Accounting, Asset, and Budgeting Policies |  | Reporting, Budgeting, Assets | Low | Open
Prepare and Execute Companywide Training on Changes |  | Reporting, Budgeting, Assets | Low | Open
Prepare Audit Support for Changes to Policies, Principles, Etc. |  | Reporting, Budgeting, Assets | Low | Open
Design and Implement New/Altered Monthly Close Process |  | Reporting, Budgeting, Assets | Low | Open
Design and Implement New/Altered Reporting Process, Including Historical Comparatives and Management Discussion/Analysis |  | Reporting, Budgeting, Assets | Low | Open
Create Plan for Historical Accounting, Asset, and Budget Data Retention and Reporting for Tax and Audit Purposes |  | Reporting, Budgeting, Assets | Low | Open
Evaluate Diligence Material for Spending Patterns |  | Transition Procure to Pay | Low | Open
Evaluate Vendor Contracts, Including Contracts for Contingent Staff/Consultants, Make Strategic Sourcing Determinations |  | Transition Procure to Pay | Low | Open
Create Plan for Contract Novation, Cancellation, or Replacement for Each Vendor |  | Transition Procure to Pay | Low | Open
Evaluate Open Purchase Orders and Purchase Commitments and Create Transition Plan |  | Transition Procure to Pay | Low | Open
Create Plan for Pre-Close Invoice Settlement (Migrate or Settle In Place) |  | Transition Procure to Pay | Low | Open
Create Plan for Historical Procurement and Payables Data Retention and Reporting for Tax and Audit Purposes |  | Transition Procure to Pay | Low | Open
Setup Tax Reporting and Compliance for Vendors Where Necessary, Including Integration Into Any Tax Calculators/Systems |  | Transition Procure to Pay | Low | Open
Setup New Vendors |  | Transition Procure to Pay | Low | Open
Migrate Open Purchase Orders |  | Transition Procure to Pay | Low | Open
Integrate P-Card, Company Credit Card Programs |  | Transition Procure to Pay | Low | Open
Establish Combined Procurement Policies and Procedures, Including Approval Matrices |  | Transition Procure to Pay | Low | Open
Prepare and Execute Companywide Training on Changes to Policies/Procedures |  | Transition Procure to Pay | Low | Open
Coordinate with Change Management and Communications on Vendor Communications and Outreach |  | Transition Procure to Pay | Low | Open
Evaluate Diligence Material for Purchasing and Collection Patterns |  | Transition Credit, Invoicing, Collections | Low | Open
Evaluate Credit and Collections Policies |  | Transition Credit, Invoicing, Collections | Low | Open
Evaluate Customer Contracts for Financing, Payment, and Collections Terms |  | Transition Credit, Invoicing, Collections | Low | Open
Coordinate with Sales/BU on Customer Contract Novation Approach, Including Approach to Common Customers |  | Transition Credit, Invoicing, Collections | Low | Open
Evaluate Any Factoring or Other Receivables Financing Arrangements |  | Transition Credit, Invoicing, Collections | Low | Open
Create Plan for Pre-Close Invoice Settlement (Migrate or Settle In Place) |  | Transition Credit, Invoicing, Collections | Low | Open
Setup Acquired Customers |  | Transition Credit, Invoicing, Collections | Low | Open
Migrate Open Sales Orders |  | Transition Credit, Invoicing, Collections | Low | Open
Create Plan for Historical Credit, Sales, and Collections Data Retention and Reporting for Tax and Audit Purposes |  | Transition Credit, Invoicing, Collections | Low | Open
Setup Tax Reporting and Compliance for Customers Where Necessary, Including Integration Into Any Tax Calculators/Systems |  | Transition Credit, Invoicing, Collections | Low | Open
Establish Combined Procurement Policies and Procedures, Including Credit/Financing Terms |  | Transition Credit, Invoicing, Collections | Low | Open
Prepare and Execute Companywide Training on Changes to Policies/Procedures |  | Transition Credit, Invoicing, Collections | Low | Open
Coordinate with Change Management, Communications, and Sales on Customer Communications and Outreach |  | Transition Credit, Invoicing, Collections | Low | Open
Evaluate Diligence Material for Banking Information Including Accounts, Signatories, Transfer/Sweep Arrangements, Etc. |  | Treasury and Cash Management | Low | Open
Evaluate Diligence Material for Financial Contracts/Options/Hedges and Develop Transition Approach |  | Treasury and Cash Management | Low | Open
Evaluate Diligence Material for Other Financial Instruments/Investments and Develop Transition Approach |  | Treasury and Cash Management | Low | Open
Evaluate Restricted Cash Requirements (Deposits, Balance Arrangements, Etc.) and Develop Transition Approach |  | Treasury and Cash Management | Low | Open
Evaluate Overdraft Requirements and Develop Transition Approach |  | Treasury and Cash Management | Low | Open
Evaluate Short/Long Term Debt and Develop Transition Approach |  | Treasury and Cash Management | Low | Open
Finalize and Communicate Strategy and Approach for Migration of Banking Relationships, Including Determination of Signatories |  | Treasury and Cash Management | Low | Open
Evaluate Payables and Receivables Workflows and Processes for Congruence with Banking Strategy |  | Treasury and Cash Management | Low | Open
Ensure Appropriate Users are Setup/Cutoff in Banking Systems, and that Systems Include Any New/Altered Accounts |  | Treasury and Cash Management | Low | Open
Integrate Cash Forecasting and Reporting Processes |  | Treasury and Cash Management | Low | Open
Integrate Hedging Processes |  | Treasury and Cash Management | Low | Open
Evaluate Diligence Material for Direct and Indirect Tax Arrangements/Obligations and Filing Groups |  | Transition Tax and Legal Entity | Low | Open
Evaluate Diligence Material for Statutory Reporting Obligations |  | Transition Tax and Legal Entity | Low | Open
Evaluate Diligence Material for Legal Entity Structure |  | Transition Tax and Legal Entity | Low | Open
Evaluate Diligence Material for Carryforwards/Carrybacks |  | Transition Tax and Legal Entity | Low | Open
Evaluate Diligence Material for any Tax, Customs, or Development Incentives or Arrangements, Including Bonding and Incentive Zones |  | Transition Tax and Legal Entity | Low | Open
Evaluate Fiscal Year Ramifications |  | Transition Tax and Legal Entity | Low | Open
Develop Tax and Legal Entity Step Plan, Including Addressing Tax Ramifications of Capital Stack for Transaction |  | Transition Tax and Legal Entity | Low | Open
Setup/Close Legal Entities as Described by Step Plan |  | Transition Tax and Legal Entity | Low | Open
Develop Transfer Pricing and Intercompany Agreements |  | Transition Tax and Legal Entity | Low | Open
Prepare Required Statutory/Tax Authority Notifications, Including Transfer Pricing, Filing Group Changes, and Changes to Filing Periods |  | Transition Tax and Legal Entity | Low | Open
Ensure All Entities and Parameters are Properly Implemented in Tax Systems |  | Transition Tax and Legal Entity | Low | Open
Create Plan for Historical Tax, Customs, Statutory, and Legal Entity Data Retention and Reporting |  | Transition Tax and Legal Entity | Low | Open
Document Achievement of Integration Program Exit Criteria |  | Program Exit | Low | Open
Ensure All Critical Dependencies on the Project Plan Have Been Cleared |  | Program Exit | Low | Open
Document All Lessons Learned and Participate In Program Lessons Learned Readout |  | Program Exit | Low | Open
Archive All Program Documentation for Use On Future Transactions |  | Program Exit | Low | Open
Request Permission for Transition to Run-The-Business from Integration Leadership |  | Program Exit | Low | Open
Get Business Owner Sign-Off for All Remaining Transition Tasks |  | Program Exit | Low | Open
Notify Integration Leadership, Change Management, and Communications of Exit and Provide Run-The-Business Points of Contact |  | Program Exit | Low | Open