## Sheet1
Office Move Checklist
| Task | Responsibility | Due Date | Comments
1 | Negotiate new space/lease
2 | Arrange approval/signoff of new lease
3 | Organise designers for new floor plan design
4 | Advise employees of packing and moving schedule
5 | Choose Project Manager and contractors for build work
6 | Identify location of printers and workstations
7 | Identify fax machine location/s
8 | Identify copier location/s
9 | Approve floor plan
10 | Schedule and approve timeline
11 | Identify if additional furniture needs to be purchased
12 | Schedule wiring/cabling
13 | Schedule workstation assembly
14 | Define printer relocation requirements
15 | Schedule office furniture delivery
16 | Define phone equipment requirements
17 | Order phone equipment upgrade (if any)
18 | Schedule phone software changes
19 | Schedule the move
20 | Organise IT resources for the move
21 | Organise moving resources (external and internal)
22 | Organise department resources for the move
23 | Do the build work
24 | Modify network setups for new printers
25 | Modify network for new workstations
26 | Complete the wiring and cabling
27 | Install dedicated power for copiers
28 | Install new workstations
29 | Install new office furniture
30 | Send "Move Memo" to relocating employees
31 | Advise employees of packing and moving schedule
32 | Supply employees with boxes
33 | Make the phone software setup changes
34 | Install new workstations
35 | Install new phones
36 | Test telephones and IT points
37 | Transfer printer/s
38 | Transfer fax machine/s
39 | Transfer photocopier/s
40 | Transfer relocatable phone handsets
41 | Test all devices for connectivity
42 | Advise employees re procedure for empty boxes
43 | Move!
44 | Organise for clean up of old office space
45 | Return/recycle empty boxes to supplier