## Quick Inflation Factor Update
LOCATION: |  | X
PROJECT TITLE: |  | X
ENR Index
2023-01-01 | 7976.68 | Base Date | 2023-01-01
2029-07-01 | 14068.0911 | Escalation Date | 2029-07-01
1.7637 |  | Escsalation Factor (Value) | 1.7637
REVISED ESTIMATE |  |  | ORIGINAL ESTIMATE
0 |  | Construction Cost (Unescalated) | 0
0 |  | Hazardous Materials (Unescalated) | 0
0 |  | Construction Total (Unescalated) | 0
0 | 0% | Design Contingency | 0
0 | 0% | General Conditions | 0
0 | 0% | Overhead & Profit (OH&P) | 0
0 |  | Total Construction (Unescalated) | 0
0 | 1.7637 | ENR Escalation Factor and Escalated Budget Estimate | 0
0 |  | Total Construction (Escalated) | 0
0 |  | Construction Budget Total | 0
0 |  | Design Fees (Basic) | 0
0 |  | Design Fees (Other) | 0
0 |  | Design Fees Budget Total | 0
0 |  | Contingency | 0
0 |  | Management Fees | 0
0 |  | FF&E: Owner Furnished, Contractor Installed (OFCI) | 0
0 |  | FF&E: Owner Furnished, Owner Installed (OFOI) | 0
0 |  | Furnishings, Fixtures, & Equipment Budget (FF&E) Total | 0
0 |  | TOTAL BUDGET | 0
Notes:
This worksheet references data from the [PBW] and [PBW_Summary] worksheets. It is intended to provide a quick budget estimate based on updated ENR Building Cost Index values when they are published in subsequent PBW templates. The current budget estimate is based on the Inflation Factor displayed in cells [A6] and [B17]. Assuming no other changes to the PBW content other than ENR Index values, the value in cell [B17] may be overwritten based on the new Inflation Factor contained in subsequent PBW templates. Simply open the newest PBW template and find the current Inflation Factor calculated for the specified Based Date and Bid Date in the [ENR] worksheet, which is located in the cell reference displayed in cell [A7]. Enter that new Inflation Factor value in cell [B17] in this workbook, and the new project budget estimate will be calculated and updated to current ENR Index standards.
Note on B18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please use the current PBW template to find an updated escalation factor based on Base Date, Bid Date, and more current ENR Index values published after this file's PBW Revision Date. This allows a quick one cell and one value edit to update a previous budget estimate without having to recreate the entire PBW again, assuming all that has changed is inflation.

## Quick Inflation Date Update
LOCATION: |  | X
PROJECT TITLE: |  | X
ENR Index
2023-01-01 | 7976.68 | Base Date | 2023-01-01
2029-07-01 | 14068.0911 | Bid Date (can be manually overwritten) | 2029-07-01
1.7637 |  | Escalation Factor (Value) | 1.7637
REVISED ESTIMATE |  |  | ORIGINAL ESTIMATE
0 |  | Construction Cost (Unescalated) | 0
0 |  | Hazardous Materials (Unescalated) | 0
0 |  | Construction Total (Unescalated) | 0
0 | 0% | Design Contingency | 0
0 | 0% | General Conditions | 0
0 | 0% | Overhead & Profit (OH&P) | 0
0 |  | Total Construction (Unescalated) | 0
0 | 1.7637 | ENR Escalation Factor and Escalated Budget Estimate | 0
0 |  | Total Construction (Escalated) | 0
0 |  | Construction Budget Total | 0
0 |  | Design Fees (Basic) | 0
0 |  | Design Fees (Other) | 0
0 |  | Design Fees Budget Total | 0
0 |  | Contingency | 0
0 |  | Management Fees | 0
0 |  | FF&E: Owner Furnished, Contractor Installed (OFCI) | 0
0 |  | FF&E: Owner Furnished, Owner Installed (OFOI) | 0
0 |  | Furnishings, Fixtures, & Equipment Budget (FF&E) Total | 0
0 |  | TOTAL BUDGET | 0
Notes:
This worksheet references data from the [PBW] and [PBW_Summary] worksheets. It is intended to provide a quick budget estimate based on updated ENR Building Cost Index values when they are published in subsequent PBW templates. The current budget estimate is based on the Inflation Factor displayed in cells [A6] and [B17]. Changing the Inflation Date value in cell [A5], which defaults to the Projected Bid Date value from the [PBW] worksheet cell [H11], will change the Inflation Factor used in calculating the budget estimate in cells [A6] and [B17]. This methodology assumes no other changes to PBW content values other than the ENR Index values corresponding to the new Inflation Date.

## PBW_Summary
THE UNIVERSITY OF WISCONSIN SYSTEM | [6 empty] | PROJECT BUDGET WORKSHEET SUMMARY Rev. 2023-03 | CONSTRUCTION COST ANALYSIS: CONSTRUCTION COST ESCALATION VALUE CALCULATION
[8 empty] | 0 |  | NEW CONSTRUCTION & REMODELING COST SUBTOTAL
PROJECT TITLE: | X |  |  |  | Date Prepared: |  | 2023-03-01 16:54 | 0 |  | DEMOLITION SUBTOTAL
LOCATION: | X |  |  |  | Prepared By: |  | XXX | 0 |  | ADDITIONAL CONSTRUCTION & REMODELING COST SUBTOTAL
PROJECT TYPE: | UNSPECIFIED |  |  |  | Revised By: |  | XXX | 0 |  | FF&E: CONTRACTOR FURNISHED, CONTRACTOR INSTALLED (CFCI) SUBTOTAL
OPTION NO.: | X |  |  |  | TOT PROJ COST EST: |  | 0 | 0 |  | CONSTRUCTION & REMODELING COST SUBTOTAL
[8 empty] | 0 | 0% | DESIGN CONTINGENCY
NEW BUILDING AREA | [7 empty] | 0 | 0% | OVERHEAD & PROFIT (OH&P)
ASF New Const | 0 |  |  |  | Base Date: |  | 2023-01-01 | 0 |  | HAZARDOUS MATERIALS ABATEMENT
GSF New Const | 0 | 0% | Efficiency |  | Base Date Index: |  | 7976.68 | 0 |  | UNESCALATED CONSTRUCTION COST SUBTOTAL
[5 empty] | Escalation Date: |  | 2029-07-01 | 0 | 1.7637 | ESCALATED CONSTRUCTION COST SUBTOTAL
[5 empty] | Escalation Date Index: |  | 14068.0911 | 0 |  | ESCALATION INCLUDED IN CONSTRUCTION COST SUBTOTAL
REMODELING AREA |  |  |  |  | Escalation Factor: |  | 1.7637
GSF Remodeling | 0 | [6 empty] | FURNISHINGS, FIXTURES, & EQUIPMENT COST ANALYSIS
GSF Total Bldg | 0 | 0% | Remodeling |  | Occupancy Date: |  |  | 0 |  | FF&E: CONTRACTOR FURNISHED, CONTRACTOR INSTALLED (CFCI)
[8 empty] | 0 | 0% | FF&E: OWNER FURNISHED, CONTRACTOR INSTALLED (OFCI) | 0 | FF&E:OFCI DESIGN FEE
|  | 0 | /ASF: Construction Cost (building & site) |  |  |  |  | 0 | 0% | FF&E: OWNER FURNISHED, OWNER INSTALLED (OFOI) | 0 | FF&E:OFOI ALLOWANCE
|  | 0 | /GSF: Construction Cost (building & site) |  |  |  |  | 0 |  | FURNISHINGS, FIXTURES, & EQUIPMENT (FF&E) SUBTOTAL
|  | 0 | /ASF: Total Project Cost |  |  |  |  | ARCHITECT/ENGINEER DESIGN SERVICES COST ANALYSIS
|  | 0 | /GSF: Total Project Cost |  |  |  |  | 0 | 0% | BASIC SERVICES
[8 empty] | 0 | 0% | REIMBURSIBLE COSTS
[8 empty] | 0 |  | ARCHITECT/ENGINEER BASIC SERVICES SUBTOTAL
TOTAL CONSTRUCTION | [6 empty] | 0
CONSTRUCTION | [6 empty] | 0 | 0 | 0% | PRE-DESIGN
HAZARDOUS MATERIALS ABATEMENT | [6 empty] | 0 | 0 |  | LEED CERTIFICATION
[8 empty] | 0 | 0% | COMMISSIONING
TOTAL DESIGN FEES | [6 empty] | 0 | 0 |  | EIS/EIA CONSULTANT
DESIGN FEES (BASIC) | [6 empty] | 0 | 0 |  | CONSTRUCTION TESTING
DESIGN FEES (OTHER) | [6 empty] | 0 | 0 |  | TESTING & BALANCING
[8 empty] | 0 |  | CUSTOM LINE ITEMS SUBTOTAL
CONTINGENCY | [6 empty] | 0 | 0 |  | ADDITIONAL DESIGN SERVICES SUBTOTAL
MANAGEMENT FEES | [6 empty] | 0
FURNISHINGS, FIXTURES, & EQUIPMENT (FF&E) | [6 empty] | 0
OWNER FURNISHED, CONTRACTOR INSTALLED (OFCI) | [6 empty] | 0
OWNER FURNISHED, OWNER INSTALLED (OFOI) | [6 empty] | 0
TOTAL BUDGET ESTIMATE | [6 empty] | 0
CAPITAL PROJECT REQUEST "Project Budget" Table |  |  |  |  | SBC "CAPITAL BUDGET REQUEST" Table |  |  | AccessGov Data
[7 empty] | INFLATED | UNINFLATED
Construction: |  | $ | 0 | LINE 0 | DFDM Fee | $ | 0 | 0
Hazardous Materials: |  | $ | 0 | LINE 1 | Design: | $ | 0 | 0
Total Construction: |  | $ | 0 | LINE 3A | Construction: | $ | 0 | 0
Design Fees (Basic): |  | $ | 0 | LINE 3B | Contingency: | $ | 0 | 0
Design Fees (Other): |  | $ | 0 | LINE 4 | Equipment | $ | 0 | 0
Total Design Fees: |  | $ | 0 |  | Estimated Inflation | $ | 0 | 0
Contingency: |  | $ | 0 |  | TOTAL: | $ | 0 | 0
Management Fees: |  | $ | 0
Furnishings/Fixtures/Eqpt: |  | $ | 0
Total Budget Estimate: |  | $ | 0
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This worksheet will auto-complete based on Project Budget Worksheet (PBW).

## PBW
THE UNIVERSITY OF WISCONSIN SYSTEM | [6 empty] | PROJECT BUDGET WORKSHEET Rev. 2023-03
PROJECT TITLE: | X |  |  |  | Date Prepared: |  | 2023-03-01 16:54
LOCATION: | X |  |  |  | Prepared By: |  | XXX
PROJECT TYPE: | X | UNSPECIFIED |  |  | Revised By: |  | XXX
OPTION NO.: | X |  |  |  | TOTAL PROJECT COST ESTIMATE: |  | 0
NEW BUILDING AREA | [5 empty] | ENR Index # | Month/Year
ASF New Const | 0 |  |  |  | Base Date: | 7976.68 | 2023-01-01
GSF New Const | 0 | 0% | Efficiency |  | Bid Date: | 14068.0911 | 2029-07-01
[5 empty] | Escalation Factor (Calculated): |  | 1.7637
REMODELING AREA |  |  |  |  | Escalation Factor (Manual Override): |  | 1.7637
GSF Remodeling | 0 |  |  |  | Escalation Delta (Manual - Calculated): |  | 0
GSF Total Bldg | 0 | 0% | Remodeling |  | Occupancy Date:
NEW CONSTRUCTION BY SPACE TYPE
Space Category | ASF | Eff | GSF | $/GSF |  | Category Cost
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 |  | Subtotal: $ | 0
NEW CONSTRUCTION COST SUBTOTAL | [6 empty] | 0
REMODELING BY SPACE TYPE
Space Category | ASF | Eff | GSF | $/GSF |  | Category Cost
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 |  | Subtotal: $ | 0 | 0
REMODELING BY TRADE
Trade Category |  |  | GSF | $/GSF | DFD $/GSF | Trade Cost
General | Notes
Surface Treatment | X |  | 0 | 16 | 16 | 0
Minor | X |  | 0 | 56 | 56 | 0
Partial | X |  | 0 | 92 | 92 | 0
Complete | X |  | 0 | 111 | 111 | 0
Plumbing
Minor | X |  | 0 | 18 | 18 | 0
Partial | X |  | 0 | 31 | 31 | 0
Complete | X |  | 0 | 35 | 35 | 0
Special Laboratory Needs | X |  | 0 | 66 | 66 | 0
Heating, Ventilating, & Air Conditioning
Minor | X |  | 0 | 24 | 24 | 0
Partial | X |  | 0 | 51 | 51 | 0
Complete | X |  | 0 | 76 | 76 | 0
Electrical
Minor | X |  | 0 | 19 | 19 | 0
Partial | X |  | 0 | 34 | 34 | 0
Complete | X |  | 0 | 43 | 43 | 0
[5 empty] | Subtotal: $ | 0
REMODELING COST SUBTOTAL (cell H63 will highlight red if Remodeling by Space Type and Remodeling by Trade sections are both used) | [6 empty] | 0
NEW CONSTRUCTION & REMODELING COST SUBTOTAL | [6 empty] | 0
PROJECT TITLE: | X
NEW CONSTRUCTION & REMODELING COST SUBTOTAL (from page 1) | [6 empty] | 0
ADDITIONAL CONSTRUCTION & REMODELING COSTS:
HEADING NAME OR ITEM CODE | ITEM DESCRIPTION |  |  | QUANTITY | UNIT | UNIT COST | SUBTOTAL
DEMO | DEMOLITION (RAZING GROSS SQUARE FOOTAGE) |  |  | 0 | GSF | 19.8001 | 0
ADDITIONAL CONSTRUCTION & REMODELING COSTS
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
ADDITIONAL CONSTRUCTION & REMODELING COSTS: | [6 empty] | 0
FURNISHINGS, FIXTURES, & EQUIPMENT (FF&E): CONTRACTOR FURNISHED, CONTRACTOR INSTALLED (CFCI)
0
0
0
0
0
0
0
0
FF&E: CFCI | [6 empty] | 0
ADDITIONAL CONSTRUCTION & REMODELING COST SUBTOTAL | [6 empty] | 0
CONSTRUCTION & REMODELING COST SUBTOTAL | [6 empty] | 0
HAZ MATS | HAZARDOUS MATERIALS ABATEMENT |  |  | 0 | SF | 0 | 0
PROJECT TITLE: | X
CONSTRUCTION & REMODELING COST SUBTOTAL (from page 2) | [6 empty] | 0
1. Total Construction Cost | [6 empty] | 0
NEW CONSTRUCTION & REMODELING COST (from Page 1) |  |  |  | 0
DEMOLITION (from Page 2) |  |  |  | 0
ADDITIONAL CONSTRUCTION & REMODELING COST (from Page 2) |  |  |  | 0
FF&E: CFCI (from Page 2) |  |  |  | 0
CONSTRUCTION & REMODELING COST SUBTOTAL (from Page 2) |  |  |  | 0
Design Contingency |  | 0% | 0 | 0
General Conditions |  | 0% | 0 | 0
Overhead & Profit (OH&P) |  | 0% | 0 | 0
HAZARDOUS MATERIALS ABATEMENT (from Page 2) |  |  |  | 0
Unescalated Construction Cost Subtotal |  |  |  | 0
Escalation Factor (from Page 1) |  | 1.7637 | 0 | 0
2. Architect/Engineer Basic Services | [6 empty] | 0
Basic Services (Calculated % of Construction $) |  | 0% | 0 | 0
Basic Services (Enter Direct $ for Basic A/E Fees) |  |  |  | 0
Reimbursible costs |  | 0% | 0 | 0
3. Additional Design Services | [6 empty] | 0
Pre-design |  | 0% | 0 | 0
Sustainable/Resilient Design |  |  |  | 0
Commissioning (Level 1 or 2) |  | 0% | 0 | 0
EIS/EIA consultant |  |  |  | 0
Construction Testing |  |  |  | 0
Testing & Balancing |  |  |  | 0
Specify Additional Design Service |  |  |  | 0
Specify Additional Design Service |  |  |  | 0
Specify Additional Design Service |  |  |  | 0
Specify Additional Design Service |  |  |  | 0
Furnishings, Fixtures, & Equipment (FF&E) Design Fee |  | 0% | 0 | 0
Furnishings, Fixtures, & Equipment (FF&E): Owner Furnished, Contractor Installed (OFCI) |  |  |  |  | FF&E: OFCI | 0
Audio-Visual and Computer Equipment |  |  |  | 0
Systems Furniture |  |  |  | 0
Specify FF&E Title(s), Type(s), and Budget Estimate Lump Sum |  |  |  | 0
Specify FF&E Title(s), Type(s), and Budget Estimate Lump Sum |  |  |  | 0
Specify FF&E Title(s), Type(s), and Budget Estimate Lump Sum |  |  |  | 0
4. Project Contingency |  | 0% | 0 | 0 |  |  | 0
5. Project Management |  | 0% | 0 | 0 |  |  | 0
6. Furnishings, Fixtures, & Equipment (FF&E) | [6 empty] | 0
FF&E: OFCI (from #3 above) |  |  |  | 0
Furnishings, Fixtures, & Equipment (FF&E): Owner Furnished, Owner Installed (OFOI) |  |  |  |  | FF&E: OFOI | 0
Movable & Special Equipment (% of Construction $) |  | 0% | 0 | 0
Audio-Visual and Computer Equipment |  |  |  | 0
Systems Furniture |  |  |  | 0
Specify Equipment Title(s), Type(s), and Budget Estimate Lump Sum |  |  |  | 0
Specify Equipment Title(s), Type(s), and Budget Estimate Lump Sum |  |  |  | 0
Specify Equipment Title(s), Type(s), and Budget Estimate Lump Sum |  |  |  | 0
TOTAL PROJECT BUDGET ESTIMATE | [6 empty] | 0
|  | 0 | /ASF: Construction Cost (building & site)
|  | 0 | /GSF: Construction Cost (building & site)
|  | 0 | /ASF: Total Project Cost
|  | 0 | /GSF: Total Project Cost
NOTES:
X
X
X
X
X
Note on H3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The contents in this cell should be hard coded to the date the PBW is finalized. Simply overwrite the formula with the actual date entry (i.e. 04/01/2022).
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Intended to contain the UW Institution Name (i.e. UNIVERSITY OF WISCONSIN-INSTITUTION NAME).
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AA = All Agency IS = Instructional Space MFR = Minor Facilities Renewal MP = Major Project P&D = Planning & Design SP = Small Project X = Unspecified
Note on B6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Intended to contain the Project Name, Project No., Alternate or Option No., and date reference of publication.
Note on H9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Base Date should be on or prior to revision date of Project Budget Worksheet template to maximize the actual inflation included in the budget estimate vs. estimated inflation. Cell has conditional formatting to highlight RED if Base Date > PBW Revision Date or if Base Date is more than 4 years old, highlight YELLOW if the Base Date is between 2-4 years old.
Note on H12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This value will default to the Escalation (Calculated) value above based on the Base Date and Bid Date values embedded in the ENR Index worksheet included in this workbook template. This value can be manually overwritten using the ENR Index values from a future Project Budget Worksheet edition to correct inflation value calculations and estimates after the initial Project Budget Worksheet creation and submittal.
Note on H14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Occupancy Date will autocalculate based on project size and DFD guidance on project duration based on project size.
Note on F41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DFD Standard Trade Unit Costs: Automatically updated based on July 2011 ENR Value and the PBW Base Index Value defined above.
Note on G69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DFD Standard Demolition Cost: Automatically updated based on July 2018 ENR Value and the PBW Base Index Value defined above.
Note on C134: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Default to 10%, but may range above or below that value dependent on size, complexity, and development status of project. Use Designer's value from feasibility study when possible. Value should be 0% if Design Report is complete.
Note on C135: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indirect project costs, project specific costs that do not result in an asset. Use Desiger's value from Pre-Design Report when necessary (i.e. when pre-design values that are used in PBW do not already include General conditions factors).
Note on C136: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indirect non-project costs. Typically ranges from 5% to 15%. Use Desiger's value from Pre-Design Report when necessary (i.e. when pre-design values that are used in PBW do not already include OH&P factors).
Note on C142: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New Construction Design Fee Guidance Project Complexity Construction Cost HIGH ¦ AVG ¦ LOW ≦ $100K: (14.2% ¦ 13.6% ¦ 12.8%) $100K - $500K: (14.1% ¦ 13.3% ¦ 12.3%) $500K - $1M: (11.6% ¦ 10.9% ¦ 9.9%) $1M - $2.5M: (10.6% ¦ 9.8% ¦ 8.8%) $2.5M - $5M: ( 9.2% ¦ 8.3% ¦ 7.3%) $5M - $30M: ( 8.3% ¦ 7.4% ¦ 6.3%) $30M - $50M: ( 7.0% ¦ 6.2% ¦ 5.3%) $50M+: ( 6.1% ¦ 5.5% ¦ 4.7%) Renovation & Remodeling Design Fee Guidance Project Complexity Construction Cost HIGH ¦ AVG ¦ LOW ≦ $100K: (16.0% ¦ 14.0% ¦ 13.0%) $100K - $500K: (14.3% ¦ 13.5% ¦ 12.5%) $500K - $1M: (12.0% ¦ 11.1% ¦ 10.1%) $1M - $2.5M: (10.9% ¦ 9.9% ¦ 8.9%) $2.5M - $5M: ( 9.4% ¦ 8.5% ¦ 7.4%) $5M - $30M: ( 8.4% ¦ 7.5% ¦ 6.4%) $30M - $50M: ( 7.1% ¦ 6.3% ¦ 5.4%) $50M+: ( 6.2% ¦ 5.6% ¦ 4.8%) If programming is not done by the agency, or if extensive program verification is required, an additional 0.1% to 1.5% should be added to the fee guidance shown above. High Complexity: Most complex projects both in design and detail include buildings of specialized architectural character, memorial, historic or monumental nature requiring special study or analysis and/or involve complex programs, mechanical systems, code requirements, etc. Project types include auditorium/theaters, communication buildings, extended care facilities, complex engineering projects, laboratories, historical restoration, and museums. Average Complexity: Project types include readiness centers, building systems, maintenance shops, firing ranges, recreational facilities, teaching laboratories, medical offices & clinics, laundry facilities, office buildings, site utilities, university centers, residence halls, and child day care facilities. Low Complexity: Projects are simple or repetitive construction without any great degree of special finish or design effort. May include projects where equipment purchase comprises a large portion of the construction budget. Project types include asbestos removal, building envelope repairs, roofing, life safety compliance, demolition, minimum security correctional centers, park shelters, warehouse, radio/television towers, service garage, and site work.
Note on E143: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data Entry in this cell will override the calculated Fee in the Row above based on the % of Construction Cost. This cell can be used for Fees only type projects (i.e. Feasibility Studies, Master Plans, etc.) or when the user needs to match a specific $ amount that is easier to enter than to calculate.
Note on C144: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Normally 4% of A/E fee for Major Projects. Includes survey, geotechnical, and plan review.
Note on C147: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ranges from 1/2% to 1-1/4% for Major Projects.
Note on C149: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Level 1 = 0.00% - 0.25% Level 2 = 0.15% - 1.00%
Note on E150: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Type I: $50,000 - $100,000 Type II: $30,000 - $50,000
Note on C157: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This Design Fee is a percent of the OFCI Furnishings, Fixtures, & Equipment Cost Estimate. Percentages will vary based on complexity of project, FF&E items, and services desired. ≤4% of FF&E Budget: Selection and specification only. ≤10% of FF&E Budget: Selection, specification, layout/design, and procurement assistance. REQUIRES DATA ENTRY IN ONE OR MORE OF THE FIVE ROWS IMMEDIATELY BELOW THIS ROW.
Note on C165: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Percent of Total Construction Cost. 15% default for all projects.
Note on E167: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4% of (Total Construction Cost + Project Contingency).
Note on C172: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lump sum percentage of construction value + the itemized costs in the five rows below this row. Percentages will vary based on project type, how much existing FF&E will be salvaged, etc. - Typical project 5-10% - Laboratory buildings 10-15%

## PBW_Summary_NoInflation
THE UNIVERSITY OF WISCONSIN SYSTEM | [6 empty] | PROJECT BUDGET WORKSHEET SUMMARY (NO INFLATION) Rev. 2023-03
PROJECT TITLE: | X |  |  |  | Date Prepared: |  | 2023-03-01 16:54
LOCATION: | X |  |  |  | Prepared By: |  | XXX
PROJECT TYPE: | UNSPECIFIED |  |  |  | Revised By: |  | XXX
OPTION NO.: | X |  |  |  | TOT PROJ COST EST: |  | 0
NEW BUILDING AREA
ASF New Const | 0 |  |  |  | Base Date: |  | 2023-01-01
GSF New Const | 0 | 0% | Efficiency |  | Base Date Index: |  | 7976.68
[5 empty] | Escalation Date: |  | 2029-07-01
[5 empty] | Escalation Date Index: |  | 14068.0911
REMODELING AREA |  |  |  |  | Escalation Factor: |  | 1.7637
GSF Remodeling | 0
GSF Total Bldg | 0 | 0% | Remodeling |  | Occupancy Date:
|  | 0 | /ASF: Construction Cost (building & site)
|  | 0 | /GSF: Construction Cost (building & site)
|  | 0 | /ASF: Total Project Cost
|  | 0 | /GSF: Total Project Cost
TOTAL CONSTRUCTION | [6 empty] | 0
CONSTRUCTION | [6 empty] | 0
HAZARDOUS MATERIALS ABATEMENT | [6 empty] | 0
TOTAL DESIGN FEES | [6 empty] | 0
DESIGN FEES (BASIC) | [6 empty] | 0
DESIGN FEES (OTHER) | [6 empty] | 0
CONTINGENCY | [6 empty] | 0
MANAGEMENT FEES | [6 empty] | 0
FURNISHINGS, FIXTURES, & EQUIPMENT (FF&E) | [6 empty] | 0
OWNER FURNISHED, CONTRACTOR INSTALLED (OFCI) | [6 empty] | 0
OWNER FURNISHED, OWNER INSTALLED (OFOI) | [6 empty] | 0
TOTAL BUDGET ESTIMATE | [6 empty] | 0
CAPITAL PROJECT REQUEST "Project Budget" Table (NO INFLATION) |  |  |  |  | SBC "CAPITAL BUDGET REQUEST" Table
INFLATED
Construction: |  | $ | 0 | LINE 0 | DFDM Fee | $ | 0
Hazardous Materials: |  | $ | 0 | LINE 1 | Design: | $ | 0
Total Construction: |  | $ | 0 | LINE 3A | Construction: | $ | 0
Design Fees (Basic): |  | $ | 0 | LINE 3B | Contingency: | $ | 0
Design Fees (Other): |  | $ | 0 | LINE 4 | Equipment | $ | 0
Total Design Fees: |  | $ | 0 |  | Estimated Inflation | $ | 0
Contingency: |  | $ | 0 |  | TOTAL: | $ | 0
Management Fees: |  | $ | 0
Furnishings/Fixtures/Eqpt: |  | $ | 0
Total Budget Estimate: |  | $ | 0
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This worksheet will auto-complete based on Project Budget Worksheet (PBW).

## PBW_NoInflation
THE UNIVERSITY OF WISCONSIN SYSTEM | [6 empty] | PROJECT BUDGET WORKSHEET (NO INFLATION) Rev. 2023-03
PROJECT TITLE: | X |  |  |  | Date Prepared: |  | 2023-03-01 16:54
LOCATION: | X |  |  |  | Prepared By: |  | XXX
PROJECT TYPE: | UNSPECIFIED |  |  |  | Revised By: |  | XXX
OPTION NO.: | X |  |  |  | TOTAL PROJECT COST ESTIMATE: |  | 0
NEW BUILDING AREA | [5 empty] | ENR Index # | Month/Year
ASF New Const | 0 |  |  |  | Base Date: | 7976.68 | 2023-01-01
GSF New Const | 0 | 0% | Efficiency |  | Escalation Date: | 14068.0911 | 2029-07-01
[5 empty] | Escalation Factor (Calculated): |  | 1.7637
REMODELING AREA |  |  |  |  | Escalation Factor (Manual Override): |  | 1.7637
GSF Remodeling | 0 |  |  |  | Escalation Delta (Manual - Calculated): |  | 0
GSF Total Bldg | 0 | 0% | Remodeling |  | Occupancy Date:
NEW CONSTRUCTION BY SPACE TYPE
Space Category | ASF | Eff | GSF | $/GSF |  | Category Cost
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 |  | Subtotal: $ | 0
NEW CONSTRUCTION COST SUBTOTAL | [6 empty] | 0
REMODELING BY SPACE TYPE
Space Category | ASF | Eff | GSF | $/GSF |  | Category Cost
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 |  | Subtotal: $ | 0 | 0
REMODELING BY TRADE
Trade Category |  |  | GSF | $/GSF | DFDM $/GSF | Trade Cost
General | Notes
Surface Treatment | X | 0 | 0 | 16 | 16 | 0
Minor | X | 0 | 0 | 56 | 56 | 0
Partial | X | 0 | 0 | 92 | 92 | 0
Complete | X | 0 | 0 | 111 | 111 | 0
Plumbing
Minor | X | 0 | 0 | 18 | 18 | 0
Partial | X | 0 | 0 | 31 | 31 | 0
Complete | X | 0 | 0 | 35 | 35 | 0
Special Laboratory Needs | X | 0 | 0 | 66 | 66 | 0
Heating, Ventilating, & Air Conditioning
Minor | X | 0 | 0 | 24 | 24 | 0
Partial | X | 0 | 0 | 51 | 51 | 0
Complete | X | 0 | 0 | 76 | 76 | 0
Electrical
Minor | X | 0 | 0 | 19 | 19 | 0
Partial | X | 0 | 0 | 34 | 34 | 0
Complete | X | 0 | 0 | 43 | 43 | 0
[5 empty] | Subtotal: $ | 0
REMODELING COST SUBTOTAL (cell H63 will highlight red if Remodeling by Space Type and Remodeling by Trade sections are both used) | [6 empty] | 0
NEW CONSTRUCTION & REMODELING COST SUBTOTAL | [6 empty] | 0
PROJECT TITLE: | X
NEW CONSTRUCTION & REMODELING COST SUBTOTAL (from page 1) | [6 empty] | 0
ADDITIONAL CONSTRUCTION & REMODELING COSTS:
HEADING NAME OR ITEM CODE | ITEM DESCRIPTION |  |  | QUANTITY | UNIT | UNIT COST | SUBTOTAL
DEMO | DEMOLITION (RAZING GROSS SQUARE FOOTAGE) |  |  | 0 | GSF | 19.8001 | 0
ADDITIONAL CONSTRUCTION & REMODELING COSTS
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
ADDITIONAL CONSTRUCTION & REMODELING COSTS: | [6 empty] | 0
FURNISHINGS, FIXTURES, & EQUIPMENT (FF&E): CONTRACTOR FURNISHED, CONTRACTOR INSTALLED (CFCI)
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FF&E: CFCI | [6 empty] | 0
ADDITIONAL CONSTRUCTION & REMODELING COST SUBTOTAL | [6 empty] | 0
CONSTRUCTION & REMODELING COST SUBTOTAL | [6 empty] | 0
HAZ MATS | HAZARDOUS MATERIALS ABATEMENT |  |  | 0 | SF | 0 | 0
PROJECT TITLE: | X
CONSTRUCTION & REMODELING COST SUBTOTAL (from page 2) | [6 empty] | 0
1. Total Construction Cost | [6 empty] | 0
NEW CONSTRUCTION & REMODELING COST (from Page 1) |  |  |  | 0
DEMOLITION (from Page 2) |  |  |  | 0
ADDITIONAL CONSTRUCTION & REMODELING COST (from Page 2) |  |  |  | 0
FF&E: CFCI (from Page 2) |  |  |  | 0
CONSTRUCTION & REMODELING COST SUBTOTAL (from Page 2) |  |  |  | 0
Design Contingency |  | 0% | 0 | 0
General Conditions |  | 0% | 0 | 0
Overhead & Profit (OH&P) |  | 0% | 0 | 0
HAZARDOUS MATERIALS ABATEMENT (from Page 2) |  |  |  | 0
Unescalated Construction Cost Subtotal |  |  |  | 0
Escalation Factor (NO INFLATION OPTION) |  | 1 | 0 | 0
2. Architect/Engineer Basic Services | [6 empty] | 0
Basic Services (Calculated % of Construction $) |  | 0% | 0 | 0
Basic Services (Enter Direct $ for Basic A/E Fees) |  |  |  | 0
Reimbursible costs |  | 0% | 0 | 0
3. Additional Design Services | [6 empty] | 0
Pre-design |  | 0% | 0 | 0
Sustainable/Resilient Design |  |  |  | 0
Commissioning (Level 1 or 2) |  | 0% | 0 | 0
EIS/EIA consultant |  |  |  | 0
Construction Testing |  |  |  | 0
Testing & Balancing |  |  |  | 0
Specify Additional Design Service |  |  |  | 0
Specify Additional Design Service |  |  |  | 0
Specify Additional Design Service |  |  |  | 0
Specify Additional Design Service |  |  |  | 0
Furnishings, Fixtures, & Equipment (FF&E) Design Fee |  | 0% | 0 | 0
Furnishings, Fixtures, & Equipment (FF&E): Owner Furnished, Contractor Installed (OFCI) |  |  |  |  | FF&E: OFCI | 0
Audio-Visual and Computer Equipment |  |  |  | 0
Systems Furniture |  |  |  | 0
Specify FF&E Title(s), Type(s), and Budget Estimate Lump Sum |  |  |  | 0
Specify FF&E Title(s), Type(s), and Budget Estimate Lump Sum |  |  |  | 0
Specify FF&E Title(s), Type(s), and Budget Estimate Lump Sum |  |  |  | 0
4. Project Contingency |  | 0% | 0 | 0 |  |  | 0
5. Project Management |  | 0% | 0 | 0 |  |  | 0
6. Furnishings, Fixtures, & Equipment (FF&E) | [6 empty] | 0
FF&E: OFCI (from #3 above) |  |  |  | 0
Furnishings, Fixtures, & Equipment (FF&E): Owner Furnished, Owner Installed (OFOI) |  |  |  |  | FF&E: OFOI | 0
Movable/Special Equipment (% of Construction $) |  | 0% | 0 | 0
Audio-Visual and Computer Equipment |  |  |  | 0
Systems Furniture |  |  |  | 0
Specify Eqpt Title(s), Type(s), & Budget Estimate Lump Sum |  |  |  | 0
Specify Eqpt Title(s), Type(s), & Budget Estimate Lump Sum |  |  |  | 0
Specify Eqpt Title(s), Type(s), & Budget Estimate Lump Sum |  |  |  | 0
TOTAL PROJECT BUDGET ESTIMATE | [6 empty] | 0
|  | 0 | /ASF: Construction Cost (building & site)
|  | 0 | /GSF: Construction Cost (building & site)
|  | 0 | /ASF: Total Project Cost
|  | 0 | /GSF: Total Project Cost
NOTES:
X
X
X
X
X
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This worksheet will auto-complete based on Project Budget Worksheet (PBW).

## ENR
| START A | END A |  | START B | END B
YEAR | 2022 | 2023 |  | 2024 | 2070
MONTH | 7 | 12 |  | 1 | 12
COMBO | 202207 | 202312 |  | 202401 | 207012
DATE | 2022-07-01 | 2023-12-01 |  | 2024-01-01 | 2070-12-01
| ANNUAL A | MONTHLY A |  | ANNUAL B | MONTHLY B
RATE | 16% | 1.333% |  | 8% | 0.6667%
| PROJECT REQUEST INFORMATION [PBW WORKSHEET] | [5 empty] | INDEPENDENT INFLATION FACTOR SCENARIO BUILDER INFORMATION | [5 empty] | REMODELING BY TRADE INFORMATION [PBW WORKSHEET] | [5 empty] | DEMOLITION (RAZING GROSS SQUARE FOOTAGE) INFORMATION [PBW WORKSHEET] | [5 empty] | UNIT COST ESTIMATE INFORMATION [COST GUIDELINES WORKSHEET] |  |  |  |  | INFLATION DATE UPDATE INFORMATION [QUICK INFLATION DATE UPDATE WORKSHEET]
|  | PBW BASE | PBW BID | INFLATION | FACTOR |  |  | BASE | BID | INFLATION | FACTOR |  |  | TRADE BASE | NEW BASE | INFLATION | FACTOR |  |  | DEMO BASE | NEW BASE | INFLATION | FACTOR |  |  | COST BASE | NEW BASE | INFLATION | FACTOR |  | BASE DATE | BID DATE | INFLATION | FACTOR
| YEAR | 2023 | 2029 |  |  |  | YEAR | 2023 | 2029 |  |  |  | YEAR | 2011 | 2023 |  |  |  | YEAR | 2018 | 2023 |  |  |  | YEAR | 2022 | 2023 |  |  | YEAR | 2023 | 2029
| MONTH | 1 | 7 |  |  |  | MONTH | 1 | 7 |  |  |  | MONTH | 7 | 1 |  |  |  | MONTH | 7 | 1 |  |  |  | MONTH | 12 | 3 |  |  | MONTH | 1 | 7
| COMBO | 202301 | 202907 |  |  |  | COMBO | 202301 | 202907 |  |  |  | COMBO | 201107 | 202301 |  |  |  | COMBO | 201807 | 202301 |  |  |  | COMBO | 202212 | 202303 |  |  | COMBO | 202301 | 202907
| DATE | 2023-01-01 | 2029-07-01 |  |  |  | DATE | 2023-01-01 | 2029-07-01 |  | 1.7637 |  | DATE | 2011-07-01 | 2023-01-01 |  |  |  | DATE | 2018-07-01 | 2023-01-01 |  |  |  | DATE | 2022-12-01 | 2023-03-01 |  |  | DATE | 2023-01-01 | 2029-07-01
| INDEX | 7976.68 | 14068.0911 | 76.37% | 1.7637 |  | INDEX | 7976.68 | 14068.0911 | 76.37% | 1.7637 |  | INDEX | 5074 | 7976.68 | 57.21% | 1.5721 |  | INDEX | 6042.91 | 7976.68 | 32% | 1.32 |  | INDEX | 7971.96 | 8000.61 | 0.3594% | 1.0036 | INDEX | 7976.68 | 14068.0911 | 76.37% | 1.7637
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1990 | 2664 | 2668 | 2673 | 2676 | 2691 | 2715 | 2716 | 2716 | 2730 | 2728 | 2730 | 2720 | 199001 | 199002 | 199003 | 199004 | 199005 | 199006 | 199007 | 199008 | 199009 | 199010 | 199011 | 199012
1991 | 2720 | 2716 | 2715 | 2709 | 2723 | 2733 | 2757 | 2792 | 2785 | 2786 | 2791 | 2784 | 199101 | 199102 | 199103 | 199104 | 199105 | 199106 | 199107 | 199108 | 199109 | 199110 | 199111 | 199112
1992 | 2784 | 2775 | 2799 | 2809 | 2828 | 2838 | 2845 | 2854 | 2857 | 2867 | 2873 | 2875 | 199201 | 199202 | 199203 | 199204 | 199205 | 199206 | 199207 | 199208 | 199209 | 199210 | 199211 | 199212
1993 | 2886 | 2886 | 2915 | 2976 | 3071 | 3066 | 3038 | 3014 | 3009 | 3016 | 3029 | 3046 | 199301 | 199302 | 199303 | 199304 | 199305 | 199306 | 199307 | 199308 | 199309 | 199310 | 199311 | 199312
1994 | 3071 | 3106 | 3116 | 3127 | 3125 | 3115 | 3107 | 3109 | 3116 | 3116 | 3109 | 3110 | 199401 | 199402 | 199403 | 199404 | 199405 | 199406 | 199407 | 199408 | 199409 | 199410 | 199411 | 199412
1995 | 3112 | 3111 | 3103 | 3100 | 3096 | 3095 | 3114 | 3121 | 3109 | 3117 | 3131 | 3128 | 199501 | 199502 | 199503 | 199504 | 199505 | 199506 | 199507 | 199508 | 199509 | 199510 | 199511 | 199512
1996 | 3127 | 3131 | 3135 | 3148 | 3161 | 3178 | 3190 | 3223 | 3246 | 3284 | 3304 | 3311 | 199601 | 199602 | 199603 | 199604 | 199605 | 199606 | 199607 | 199608 | 199609 | 199610 | 199611 | 199612
1997 | 3332 | 3333 | 3323 | 3364 | 3377 | 3396 | 3392 | 3385 | 3378 | 3372 | 3350 | 3370 | 199701 | 199702 | 199703 | 199704 | 199705 | 199706 | 199707 | 199708 | 199709 | 199710 | 199711 | 199712
1998 | 3363 | 3372 | 3368 | 3375 | 3374 | 3379 | 3382 | 3391 | 3414 | 3423 | 3424 | 3419 | 199801 | 199802 | 199803 | 199804 | 199805 | 199806 | 199807 | 199808 | 199809 | 199810 | 199811 | 199812
1999 | 3425 | 3417 | 3411 | 3421 | 3422 | 3433 | 3460 | 3474 | 3504 | 3505 | 3498 | 3497 | 199901 | 199902 | 199903 | 199904 | 199905 | 199906 | 199907 | 199908 | 199909 | 199910 | 199911 | 199912
2000 | 3503 | 3523 | 3536 | 3534 | 3558 | 3553 | 3545 | 3546 | 3539 | 3547 | 3541 | 3548 | 200001 | 200002 | 200003 | 200004 | 200005 | 200006 | 200007 | 200008 | 200009 | 200010 | 200011 | 200012
2001 | 3545 | 3536 | 3541 | 3541 | 3547 | 3572 | 3625 | 3605 | 3597 | 3602 | 3596 | 3577 | 200101 | 200102 | 200103 | 200104 | 200105 | 200106 | 200107 | 200108 | 200109 | 200110 | 200111 | 200112
2002 | 3581 | 3581 | 3597 | 3583 | 3612 | 3624 | 3652 | 3648 | 3655 | 3651 | 3654 | 3640 | 200201 | 200202 | 200203 | 200204 | 200205 | 200206 | 200207 | 200208 | 200209 | 200210 | 200211 | 200212
2003 | 3648 | 3655 | 3649 | 3652 | 3660 | 3677 | 3683 | 3712 | 3717 | 3745 | 3765 | 3757 | 200301 | 200302 | 200303 | 200304 | 200305 | 200306 | 200307 | 200308 | 200309 | 200310 | 200311 | 200312
2004 | 3767 | 3802 | 3859 | 3908 | 3956 | 3996 | 4013 | 4027 | 4102 | 4129 | 4128 | 4123 | 200401 | 200402 | 200403 | 200404 | 200405 | 200406 | 200407 | 200408 | 200409 | 200410 | 200411 | 200412
2005 | 4112 | 4116 | 4127 | 4168 | 4189 | 4195 | 4197 | 4210 | 4242 | 4265 | 4312 | 4329 | 200501 | 200502 | 200503 | 200504 | 200505 | 200506 | 200507 | 200508 | 200509 | 200510 | 200511 | 200512
2006 | 4335 | 4337 | 4330 | 4335 | 4331 | 4340 | 4356 | 4359 | 4375 | 4431 | 4462 | 4441 | 200601 | 200602 | 200603 | 200604 | 200605 | 200606 | 200607 | 200608 | 200609 | 200610 | 200611 | 200612
2007 | 4432 | 4432 | 4411 | 4416 | 4475 | 4471 | 4493 | 4512 | 4533 | 4535 | 4558 | 4556 | 200701 | 200702 | 200703 | 200704 | 200705 | 200706 | 200707 | 200708 | 200709 | 200710 | 200711 | 200712
2008 | 4557 | 4556 | 4571 | 4574 | 4599 | 4640 | 4723 | 4733 | 4827 | 4867 | 4847 | 4797 | 200801 | 200802 | 200803 | 200804 | 200805 | 200806 | 200807 | 200808 | 200809 | 200810 | 200811 | 200812
2009 | 4782 | 4765 | 4767 | 4761 | 4773 | 4771 | 4762 | 4768 | 4764 | 4762 | 4757 | 4795 | 200901 | 200902 | 200903 | 200904 | 200905 | 200906 | 200907 | 200908 | 200909 | 200910 | 200911 | 200912
2010 | 4800 | 4812 | 4811 | 4817 | 4858 | 4888 | 4910 | 4905 | 4910 | 4947 | 4968 | 4970 | 201001 | 201002 | 201003 | 201004 | 201005 | 201006 | 201007 | 201008 | 201009 | 201010 | 201011 | 201012
2011 | 4969 | 5007 | 5010 | 5028 | 5035 | 5059 | 5074 | 5091 | 5098 | 5104 | 5113 | 5115 | 201101 | 201102 | 201103 | 201104 | 201105 | 201106 | 201107 | 201108 | 201109 | 201110 | 201111 | 201112
2012 | 5120 | 5122 | 5144 | 5150 | 5167 | 5170 | 5184 | 5204 | 5195 | 5204 | 5213 | 5210 | 201201 | 201202 | 201203 | 201204 | 201205 | 201206 | 201207 | 201208 | 201209 | 201210 | 201211 | 201212
2013 | 5226 | 5246 | 5249 | 5257 | 5272 | 5286 | 5281 | 5277 | 5285 | 5308 | 5317 | 5326 | 201301 | 201302 | 201303 | 201304 | 201305 | 201306 | 201307 | 201308 | 201309 | 201310 | 201311 | 201312
2014 | 5324 | 5321 | 5336 | 5357 | 5370 | 5375 | 5383 | 5390 | 5409 | 5442 | 5468 | 5480 | 201401 | 201402 | 201403 | 201404 | 201405 | 201406 | 201407 | 201408 | 201409 | 201410 | 201411 | 201412
2015 | 5497 | 5488.1 | 5487.34 | 5500.82 | 5490.44 | 5507.38 | 5510.47 | 5514.7 | 5541.1 | 5543.93 | 5563.51 | 5560.64 | 201501 | 201502 | 201503 | 201504 | 201505 | 201506 | 201507 | 201508 | 201509 | 201510 | 201511 | 201512
2016 | 5561.76 | 5588.02 | 5605.55 | 5632.95 | 5637.09 | 5636.49 | 5659.51 | 5669.5 | 5657.28 | 5681.63 | 5690.35 | 5722.81 | 201601 | 201602 | 201603 | 201604 | 201605 | 201606 | 201607 | 201608 | 201609 | 201610 | 201611 | 201612
2017 | 5733.88 | 5742.06 | 5789.41 | 5801.76 | 5815.76 | 5826.4 | 5844.3 | 5862.24 | 5872.8 | 5866.92 | 5901.86 | 5913.81 | 201701 | 201702 | 201703 | 201704 | 201705 | 201706 | 201707 | 201708 | 201709 | 201710 | 201711 | 201712
2018 | 5921.32 | 5932.09 | 5942.13 | 5954.16 | 5995.06 | 6004.8 | 6042.91 | 6060.07 | 6081.34 | 6092.62 | 6093.13 | 6105.29 | 201801 | 201802 | 201803 | 201804 | 201805 | 201806 | 201807 | 201808 | 201809 | 201810 | 201811 | 201812
2019 | 6107.7 | 6108.09 | 6109.67 | 6109.83 | 6111.77 | 6118.34 | 6131.42 | 6146.81 | 6146.98 | 6168.75 | 6179.22 | 6199.11 | 201901 | 201902 | 201903 | 201904 | 201905 | 201906 | 201907 | 201908 | 201909 | 201910 | 201911 | 201912
2020 | 6213.68 | 6217.29 | 6218.26 | 6233.93 | 6239.42 | 6246.69 | 6258.19 | 6267.65 | 6300.3 | 6343.55 | 6391.74 | 6445.14 | 202001 | 202002 | 202003 | 202004 | 202005 | 202006 | 202007 | 202008 | 202009 | 202010 | 202011 | 202012
2021 | 6459.83 | 6493.19 | 6545.22 | 6612.5 | 6754.51 | 6876.96 | 7006.95 | 7201.88 | 7214.29 | 7244.9 | 7255.67 | 7289.5 | 202101 | 202102 | 202103 | 202104 | 202105 | 202106 | 202107 | 202108 | 202109 | 202110 | 202111 | 202112
2022 | 7359.09 | 7457.68 | 7565.14 | 7677.45 | 7785.64 | 7889.98 | 7950.39 | 7952.5 | 7958.27 | 7965.04 | 7966.9 | 7971.96 | 202201 | 202202 | 202203 | 202204 | 202205 | 202206 | 202207 | 202208 | 202209 | 202210 | 202211 | 202212
2023 | 7976.68 | 7989.84 | 8000.61 | 8107.2848 | 8215.3819 | 8324.9204 | 8435.9193 | 8548.3982 | 8662.3769 | 8777.8752 | 8894.9136 | 9013.5124 | 202301 | 202302 | 202303 | 202304 | 202305 | 202306 | 202307 | 202308 | 202309 | 202310 | 202311 | 202312
2024 | 9073.6025 | 9134.0932 | 9194.9871 | 9256.287 | 9317.9956 | 9380.1156 | 9442.6497 | 9505.6007 | 9568.9714 | 9632.7645 | 9696.9829 | 9761.6295 | 202401 | 202402 | 202403 | 202404 | 202405 | 202406 | 202407 | 202408 | 202409 | 202410 | 202411 | 202412
2025 | 9826.707 | 9892.2184 | 9958.1665 | 10024.5543 | 10091.3847 | 10158.6606 | 10226.385 | 10294.5609 | 10363.1913 | 10432.2792 | 10501.8277 | 10571.8399 | 202501 | 202502 | 202503 | 202504 | 202505 | 202506 | 202507 | 202508 | 202509 | 202510 | 202511 | 202512
2026 | 10642.3189 | 10713.2676 | 10784.6894 | 10856.5874 | 10928.9646 | 11001.8244 | 11075.1699 | 11149.0043 | 11223.331 | 11298.1532 | 11373.4743 | 11449.2974 | 202601 | 202602 | 202603 | 202604 | 202605 | 202606 | 202607 | 202608 | 202609 | 202610 | 202611 | 202612
2027 | 11525.6261 | 11602.4636 | 11679.8133 | 11757.6788 | 11836.0633 | 11914.9704 | 11994.4035 | 12074.3662 | 12154.862 | 12235.8944 | 12317.467 | 12399.5835 | 202701 | 202702 | 202703 | 202704 | 202705 | 202706 | 202707 | 202708 | 202709 | 202710 | 202711 | 202712
2028 | 12482.2473 | 12565.4623 | 12649.2321 | 12733.5603 | 12818.4507 | 12903.907 | 12989.9331 | 13076.5326 | 13163.7095 | 13251.4676 | 13339.8107 | 13428.7428 | 202801 | 202802 | 202803 | 202804 | 202805 | 202806 | 202807 | 202808 | 202809 | 202810 | 202811 | 202812
2029 | 13518.2677 | 13608.3895 | 13699.1121 | 13790.4395 | 13882.3758 | 13974.925 | 14068.0911 | 14161.8784 | 14256.2909 | 14351.3329 | 14447.0084 | 14543.3218 | 202901 | 202902 | 202903 | 202904 | 202905 | 202906 | 202907 | 202908 | 202909 | 202910 | 202911 | 202912
2030 | 14640.2773 | 14737.8791 | 14836.1317 | 14935.0392 | 15034.6061 | 15134.8368 | 15235.7357 | 15337.3073 | 15439.556 | 15542.4864 | 15646.103 | 15750.4103 | 203001 | 203002 | 203003 | 203004 | 203005 | 203006 | 203007 | 203008 | 203009 | 203010 | 203011 | 203012
2031 | 15855.4131 | 15961.1158 | 16067.5233 | 16174.6401 | 16282.471 | 16391.0208 | 16500.2943 | 16610.2963 | 16721.0316 | 16832.5051 | 16944.7218 | 17057.6866 | 203101 | 203102 | 203103 | 203104 | 203105 | 203106 | 203107 | 203108 | 203109 | 203110 | 203111 | 203112
2032 | 17171.4045 | 17285.8806 | 17401.1198 | 17517.1272 | 17633.9081 | 17751.4675 | 17869.8106 | 17988.9427 | 18108.8689 | 18229.5947 | 18351.1254 | 18473.4662 | 203201 | 203202 | 203203 | 203204 | 203205 | 203206 | 203207 | 203208 | 203209 | 203210 | 203211 | 203212
2033 | 18596.6226 | 18720.6001 | 18845.4041 | 18971.0402 | 19097.5138 | 19224.8305 | 19352.9961 | 19482.016 | 19611.8961 | 19742.6421 | 19874.2597 | 20006.7548 | 203301 | 203302 | 203303 | 203304 | 203305 | 203306 | 203307 | 203308 | 203309 | 203310 | 203311 | 203312
2034 | 20140.1331 | 20274.4007 | 20409.5634 | 20545.6271 | 20682.598 | 20820.482 | 20959.2852 | 21099.0137 | 21239.6738 | 21381.2717 | 21523.8135 | 21667.3056 | 203401 | 203402 | 203403 | 203404 | 203405 | 203406 | 203407 | 203408 | 203409 | 203410 | 203411 | 203412
2035 | 21811.7543 | 21957.166 | 22103.5471 | 22250.9041 | 22399.2434 | 22548.5717 | 22698.8955 | 22850.2215 | 23002.5563 | 23155.9067 | 23310.2794 | 23465.6812 | 203501 | 203502 | 203503 | 203504 | 203505 | 203506 | 203507 | 203508 | 203509 | 203510 | 203511 | 203512
2036 | 23622.1191 | 23779.5999 | 23938.1306 | 24097.7181 | 24258.3696 | 24420.092 | 24582.8926 | 24746.7786 | 24911.7571 | 25077.8355 | 25245.0211 | 25413.3212 | 203601 | 203602 | 203603 | 203604 | 203605 | 203606 | 203607 | 203608 | 203609 | 203610 | 203611 | 203612
2037 | 25582.7434 | 25753.295 | 25924.9836 | 26097.8168 | 26271.8023 | 26446.9476 | 26623.2606 | 26800.749 | 26979.4207 | 27159.2835 | 27340.3454 | 27522.6143 | 203701 | 203702 | 203703 | 203704 | 203705 | 203706 | 203707 | 203708 | 203709 | 203710 | 203711 | 203712
2038 | 27706.0984 | 27890.8058 | 28076.7445 | 28263.9228 | 28452.3489 | 28642.0312 | 28832.9781 | 29025.198 | 29218.6993 | 29413.4906 | 29609.5805 | 29806.9778 | 203801 | 203802 | 203803 | 203804 | 203805 | 203806 | 203807 | 203808 | 203809 | 203810 | 203811 | 203812
2039 | 30005.6909 | 30205.7289 | 30407.1004 | 30609.8144 | 30813.8798 | 31019.3057 | 31226.1011 | 31434.2751 | 31643.8369 | 31854.7958 | 32067.1611 | 32280.9422 | 203901 | 203902 | 203903 | 203904 | 203905 | 203906 | 203907 | 203908 | 203909 | 203910 | 203911 | 203912
2040 | 32496.1485 | 32712.7895 | 32930.8747 | 33150.4139 | 33371.4167 | 33593.8928 | 33817.8521 | 34043.3044 | 34270.2598 | 34498.7282 | 34728.7197 | 34960.2445 | 204001 | 204002 | 204003 | 204004 | 204005 | 204006 | 204007 | 204008 | 204009 | 204010 | 204011 | 204012
2041 | 35193.3128 | 35427.9349 | 35664.1211 | 35901.8819 | 36141.2278 | 36382.1693 | 36624.7171 | 36868.8819 | 37114.6744 | 37362.1056 | 37611.1863 | 37861.9275 | 204101 | 204102 | 204103 | 204104 | 204105 | 204106 | 204107 | 204108 | 204109 | 204110 | 204111 | 204112
2042 | 38114.3404 | 38368.436 | 38624.2256 | 38881.7204 | 39140.9319 | 39401.8714 | 39664.5506 | 39928.9809 | 40195.1741 | 40463.1419 | 40732.8962 | 41004.4489 | 204201 | 204202 | 204203 | 204204 | 204205 | 204206 | 204207 | 204208 | 204209 | 204210 | 204211 | 204212
2043 | 41277.8118 | 41552.9973 | 41830.0172 | 42108.884 | 42389.6099 | 42672.2073 | 42956.6887 | 43243.0666 | 43531.3537 | 43821.5628 | 44113.7065 | 44407.7979 | 204301 | 204302 | 204303 | 204304 | 204305 | 204306 | 204307 | 204308 | 204309 | 204310 | 204311 | 204312
2044 | 44703.8499 | 45001.8755 | 45301.888 | 45603.9006 | 45907.9266 | 46213.9795 | 46522.0727 | 46832.2198 | 47144.4346 | 47458.7309 | 47775.1224 | 48093.6232 | 204401 | 204402 | 204403 | 204404 | 204405 | 204406 | 204407 | 204408 | 204409 | 204410 | 204411 | 204412
2045 | 48414.2474 | 48737.009 | 49061.9224 | 49389.0019 | 49718.2619 | 50049.717 | 50383.3818 | 50719.271 | 51057.3994 | 51397.7821 | 51740.434 | 52085.3702 | 204501 | 204502 | 204503 | 204504 | 204505 | 204506 | 204507 | 204508 | 204509 | 204510 | 204511 | 204512
2046 | 52432.606 | 52782.1567 | 53134.0378 | 53488.2647 | 53844.8531 | 54203.8188 | 54565.1776 | 54928.9454 | 55295.1384 | 55663.7727 | 56034.8645 | 56408.4303 | 204601 | 204602 | 204603 | 204604 | 204605 | 204606 | 204607 | 204608 | 204609 | 204610 | 204611 | 204612
2047 | 56784.4865 | 57163.0497 | 57544.1367 | 57927.7643 | 58313.9494 | 58702.709 | 59094.0604 | 59488.0208 | 59884.6076 | 60283.8383 | 60685.7306 | 61090.3021 | 204701 | 204702 | 204703 | 204704 | 204705 | 204706 | 204707 | 204708 | 204709 | 204710 | 204711 | 204712
2040 | 61497.5708 | 61907.5546 | 62320.2717 | 62735.7401 | 63153.9784 | 63575.0049 | 63998.8383 | 64425.4972 | 64855.0005 | 65287.3672 | 65722.6163 | 66160.7671 | 204001 | 204002 | 204003 | 204004 | 204005 | 204006 | 204007 | 204008 | 204009 | 204010 | 204011 | 204012
2049 | 66601.8389 | 67045.8511 | 67492.8235 | 67942.7756 | 68395.7275 | 68851.699 | 69310.7103 | 69772.7817 | 70237.9336 | 70706.1865 | 71177.5611 | 71652.0781 | 204901 | 204902 | 204903 | 204904 | 204905 | 204906 | 204907 | 204908 | 204909 | 204910 | 204911 | 204912
2050 | 72129.7586 | 72610.6237 | 73094.6945 | 73581.9925 | 74072.5391 | 74566.356 | 75063.4651 | 75563.8882 | 76067.6474 | 76574.7651 | 77085.2635 | 77599.1653 | 205001 | 205002 | 205003 | 205004 | 205005 | 205006 | 205007 | 205008 | 205009 | 205010 | 205011 | 205012
2051 | 78116.493 | 78637.2697 | 79161.5181 | 79689.2616 | 80220.5233 | 80755.3268 | 81293.6957 | 81835.6536 | 82381.2247 | 82930.4328 | 83483.3024 | 84039.8577 | 205101 | 205102 | 205103 | 205104 | 205105 | 205106 | 205107 | 205108 | 205109 | 205110 | 205111 | 205112
2052 | 84600.1234 | 85164.1243 | 85731.8851 | 86303.431 | 86878.7872 | 87457.9791 | 88041.0323 | 88627.9725 | 89218.8257 | 89813.6178 | 90412.3753 | 91015.1245 | 205201 | 205202 | 205203 | 205204 | 205205 | 205206 | 205207 | 205208 | 205209 | 205210 | 205211 | 205212
2053 | 91621.892 | 92232.7046 | 92847.5893 | 93466.5732 | 94089.6837 | 94716.9482 | 95348.3946 | 95984.0505 | 96623.9442 | 97268.1038 | 97916.5579 | 98569.3349 | 205301 | 205302 | 205303 | 205304 | 205305 | 205306 | 205307 | 205308 | 205309 | 205310 | 205311 | 205312
2054 | 99226.4638 | 99887.9736 | 100553.8934 | 101224.2527 | 101899.081 | 102578.4082 | 103262.2643 | 103950.6794 | 104643.6839 | 105341.3085 | 106043.5839 | 106750.5411 | 205401 | 205402 | 205403 | 205404 | 205405 | 205406 | 205407 | 205408 | 205409 | 205410 | 205411 | 205412
2055 | 107462.2114 | 108178.6261 | 108899.8169 | 109625.8157 | 110356.6545 | 111092.3655 | 111832.9813 | 112578.5345 | 113329.0581 | 114084.5851 | 114845.149 | 115610.7834 | 205501 | 205502 | 205503 | 205504 | 205505 | 205506 | 205507 | 205508 | 205509 | 205510 | 205511 | 205512
2056 | 116381.5219 | 117157.3987 | 117938.448 | 118724.7044 | 119516.2024 | 120312.9771 | 121115.0636 | 121922.4973 | 122735.314 | 123553.5494 | 124377.2398 | 125206.4214 | 205601 | 205602 | 205603 | 205604 | 205605 | 205606 | 205607 | 205608 | 205609 | 205610 | 205611 | 205612
2057 | 126041.1308 | 126881.405 | 127727.2811 | 128578.7963 | 129435.9883 | 130298.8948 | 131167.5541 | 132042.0045 | 132922.2845 | 133808.4331 | 134700.4893 | 135598.4926 | 205701 | 205702 | 205703 | 205704 | 205705 | 205706 | 205707 | 205708 | 205709 | 205710 | 205711 | 205712
2058 | 136502.4825 | 137412.4991 | 138328.5824 | 139250.773 | 140179.1114 | 141113.6388 | 142054.3964 | 143001.4257 | 143954.7686 | 144914.467 | 145880.5635 | 146853.1006 | 205801 | 205802 | 205803 | 205804 | 205805 | 205806 | 205807 | 205808 | 205809 | 205810 | 205811 | 205812
2059 | 147832.1213 | 148817.6687 | 149809.7865 | 150808.5184 | 151813.9086 | 152826.0013 | 153844.8413 | 154870.4736 | 155902.9434 | 156942.2963 | 157988.5783 | 159041.8355 | 205901 | 205902 | 205903 | 205904 | 205905 | 205906 | 205907 | 205908 | 205909 | 205910 | 205911 | 205912
2060 | 160102.1144 | 161169.4618 | 162243.9249 | 163325.5511 | 164414.3881 | 165510.484 | 166613.8872 | 167724.6465 | 168842.8108 | 169968.4295 | 171101.5524 | 172242.2294 | 206001 | 206002 | 206003 | 206004 | 206005 | 206006 | 206007 | 206008 | 206009 | 206010 | 206011 | 206012
2061 | 173390.5109 | 174546.4477 | 175710.0907 | 176881.4913 | 178060.7012 | 179247.7726 | 180442.7577 | 181645.7094 | 182856.6808 | 184075.7254 | 185302.8969 | 186538.2495 | 206101 | 206102 | 206103 | 206104 | 206105 | 206106 | 206107 | 206108 | 206109 | 206110 | 206111 | 206112
2062 | 187781.8378 | 189033.7168 | 190293.9415 | 191562.5678 | 192839.6516 | 194125.2493 | 195419.4176 | 196722.2137 | 198033.6951 | 199353.9198 | 200682.9459 | 202020.8322 | 206201 | 206202 | 206203 | 206204 | 206205 | 206206 | 206207 | 206208 | 206209 | 206210 | 206211 | 206212
2063 | 203367.6378 | 204723.422 | 206088.2448 | 207462.1665 | 208845.2476 | 210237.5492 | 211639.1329 | 213050.0604 | 214470.3942 | 215900.1968 | 217339.5314 | 218788.4617 | 206301 | 206302 | 206303 | 206304 | 206305 | 206306 | 206307 | 206308 | 206309 | 206310 | 206311 | 206312
2064 | 220247.0514 | 221715.3651 | 223193.4675 | 224681.424 | 226179.3001 | 227687.1621 | 229205.0765 | 230733.1104 | 232271.3311 | 233819.8067 | 235378.6054 | 236947.7961 | 206401 | 206402 | 206403 | 206404 | 206405 | 206406 | 206407 | 206408 | 206409 | 206410 | 206411 | 206412
2065 | 238527.448 | 240117.631 | 241718.4152 | 243329.8713 | 244952.0705 | 246585.0843 | 248228.9848 | 249883.8447 | 251549.737 | 253226.7353 | 254914.9135 | 256614.3463 | 206501 | 206502 | 206503 | 206504 | 206505 | 206506 | 206507 | 206508 | 206509 | 206510 | 206511 | 206512
2066 | 258325.1086 | 260047.276 | 261780.9245 | 263526.1306 | 265282.9715 | 267051.5247 | 268831.8682 | 270624.0806 | 272428.2412 | 274244.4294 | 276072.7256 | 277913.2105 | 206601 | 206602 | 206603 | 206604 | 206605 | 206606 | 206607 | 206608 | 206609 | 206610 | 206611 | 206612
2067 | 279765.9652 | 281631.0716 | 283508.6121 | 285398.6695 | 287301.3273 | 289216.6695 | 291144.7806 | 293085.7458 | 295039.6508 | 297006.5818 | 298986.6257 | 300979.8699 | 206701 | 206702 | 206703 | 206704 | 206705 | 206706 | 206707 | 206708 | 206709 | 206710 | 206711 | 206712
2068 | 302986.4023 | 305006.3117 | 307039.6871 | 309086.6183 | 311147.1958 | 313221.5104 | 315309.6538 | 317411.7182 | 319527.7963 | 321657.9816 | 323802.3682 | 325961.0506 | 206801 | 206802 | 206803 | 206804 | 206805 | 206806 | 206807 | 206808 | 206809 | 206810 | 206811 | 206812
2069 | 328134.1243 | 330321.6851 | 332523.8297 | 334740.6552 | 336972.2596 | 339218.7413 | 341480.1996 | 343756.7343 | 346048.4458 | 348355.4355 | 350677.805 | 353015.6571 | 206901 | 206902 | 206903 | 206904 | 206905 | 206906 | 206907 | 206908 | 206909 | 206910 | 206911 | 206912
2070 | 355369.0948 | 357738.2221 | 360123.1436 | 362523.9645 | 364940.7909 | 367373.7295 | 369822.8877 | 372288.3737 | 374770.2962 | 377268.7648 | 379783.8899 | 382315.7825 | 207001 | 207002 | 207003 | 207004 | 207005 | 207006 | 207007 | 207008 | 207009 | 207010 | 207011 | 207012
KEY
| TEXT | ACTUAL ENR INDEX VALUE (DATA ENTRY)
| TEXT | ESTIMATED ENR INDEX VALUE (FORMULA)

## DFD Inflation Estimation Tool
2023/25 Capital Budget: Inflation Estimator
| Project Budget | 0 | Enter the estimated project budget here
| Bid Date | 2029-07-01 | Select the anticipated bid date from the drop down
| Inflation Factor | 95%
| Inflation Amount | 0
| Inflated Project Budget | 0
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This value will auto-complete based on PBW_NoInflationWorksheet.
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This value will auto-complete based on Project Budget Worksheet (PBW).

## DFD Inflation Summary
2022-06-01
2023/25 Capital Budget: Inflation Summary
| 2023-01-01 | 8% |  | 8% | 4%
| 2023-02-01 | 9.44% | 1.44% | 6 | 6
| 2023-03-01 | 10.9% | 1.459% | 1.333% | 0.6667%
| 2023-04-01 | 12.38% | 1.479%
| 2023-05-01 | 13.88% | 1.498%
| 2023-06-01 | 15.39% | 1.518%
| 2023-07-01 | 16.93% | 1.539%
| 2023-08-01 | 18.49% | 1.559%
| 2023-09-01 | 20.07% | 1.58%
| 2023-10-01 | 21.67% | 1.601%
| 2023-11-01 | 23.3% | 1.622%
| 2023-12-01 | 24.94% | 1.644%
| 2024-01-01 | 25.77% | 0.8329%
| 2024-02-01 | 26.61% | 0.8385%
| 2024-03-01 | 27.45% | 0.8441%
| 2024-04-01 | 28.3% | 0.8497%
| 2024-05-01 | 29.16% | 0.8554%
| 2024-06-01 | 30.02% | 0.8611%
| 2024-07-01 | 30.89% | 0.8668%
| 2024-08-01 | 31.76% | 0.8726%
| 2024-09-01 | 32.64% | 0.8784%
| 2024-10-01 | 33.52% | 0.8843%
| 2024-11-01 | 34.41% | 0.8902%
| 2024-12-01 | 35.31% | 0.8961%
| 2025-01-01 | 36.21% | 0.9021%
| 2025-02-01 | 37.12% | 0.9081%
| 2025-03-01 | 38.03% | 0.9141%
| 2025-04-01 | 38.95% | 0.9202%
| 2025-05-01 | 39.88% | 0.9264%
| 2025-06-01 | 40.81% | 0.9325%
| 2025-07-01 | 41.75% | 0.9388%
| 2025-08-01 | 42.7% | 0.945%
| 2025-09-01 | 43.65% | 0.9513%
| 2025-10-01 | 44.61% | 0.9577%
| 2025-11-01 | 45.57% | 0.964%
| 2025-12-01 | 46.54% | 0.9705%
| 2026-01-01 | 47.52% | 0.9769%
| 2026-02-01 | 48.5% | 0.9834%
| 2026-03-01 | 49.49% | 0.99%
| 2026-04-01 | 50.49% | 0.9966%
| 2026-05-01 | 51.49% | 1.003%
| 2026-06-01 | 52.5% | 1.01%
| 2026-07-01 | 53.52% | 1.017%
| 2026-08-01 | 54.54% | 1.023%
| 2026-09-01 | 55.57% | 1.03%
| 2026-10-01 | 56.61% | 1.037%
| 2026-11-01 | 57.65% | 1.044%
| 2026-12-01 | 58.7% | 1.051%
| 2027-01-01 | 59.76% | 1.058%
| 2027-02-01 | 60.83% | 1.065%
| 2027-03-01 | 61.9% | 1.072%
| 2027-04-01 | 62.98% | 1.079%
| 2027-05-01 | 64.06% | 1.087%
| 2027-06-01 | 65.16% | 1.094%
| 2027-07-01 | 66.26% | 1.101%
| 2027-08-01 | 67.37% | 1.108%
| 2027-09-01 | 68.48% | 1.116%
| 2027-10-01 | 69.61% | 1.123%
| 2027-11-01 | 70.74% | 1.131%
| 2027-12-01 | 71.87% | 1.138%
| 2028-01-01 | 73.02% | 1.146%
| 2028-02-01 | 74.17% | 1.153%
| 2028-03-01 | 75.34% | 1.161%
| 2028-04-01 | 76.5% | 1.169%
| 2028-05-01 | 77.68% | 1.177%
| 2028-06-01 | 78.87% | 1.185%
| 2028-07-01 | 80.06% | 1.192%
| 2028-08-01 | 81.26% | 1.2%
| 2028-09-01 | 82.47% | 1.208%
| 2028-10-01 | 83.68% | 1.216%
| 2028-11-01 | 84.91% | 1.225%
| 2028-12-01 | 86.14% | 1.233%
| 2029-01-01 | 87.38% | 1.241%
| 2029-02-01 | 88.63% | 1.249%
| 2029-03-01 | 89.89% | 1.258%
| 2029-04-01 | 91.15% | 1.266%
| 2029-05-01 | 92.43% | 1.274%
| 2029-06-01 | 93.71% | 1.283%
| 2029-07-01 | 95% | 1.291%
| 2029-08-01 | 96.3% | 1.3%
| 2029-09-01 | 97.61% | 1.309%
| 2029-10-01 | 98.93% | 1.317%
| 2029-11-01 | 100.3% | 1.326%
| 2029-12-01 | 101.6% | 1.335%
| 2030-01-01 | 102.9% | 1.344%
| 2030-02-01 | 104.3% | 1.353%
| 2030-03-01 | 105.6% | 1.362%
| 2030-04-01 | 107% | 1.371%
| 2030-05-01 | 108.4% | 1.38%
| 2030-06-01 | 109.8% | 1.389%
| 2030-07-01 | 111.2% | 1.399%
| 2030-08-01 | 112.6% | 1.408%
| 2030-09-01 | 114% | 1.417%
| 2030-10-01 | 115.4% | 1.427%
| 2030-11-01 | 116.9% | 1.436%
| 2030-12-01 | 118.3% | 1.446%
| 2031-01-01 | 119.8% | 1.455%
| 2031-02-01 | 121.2% | 1.465%
| 2031-03-01 | 122.7% | 1.475%
| 2031-04-01 | 124.2% | 1.485%
| 2031-05-01 | 125.7% | 1.495%
| 2031-06-01 | 127.2% | 1.505%
| 2031-07-01 | 128.7% | 1.515%
| 2031-08-01 | 130.2% | 1.525%
| 2031-09-01 | 131.8% | 1.535%
| 2031-10-01 | 133.3% | 1.545%
| 2031-11-01 | 134.9% | 1.555%
| 2031-12-01 | 136.4% | 1.566%
| 2032-01-01 | 138% | 1.576%
| 2032-02-01 | 139.6% | 1.587%
| 2032-03-01 | 141.2% | 1.597%
| 2032-04-01 | 142.8% | 1.608%
| 2032-05-01 | 144.4% | 1.619%
| 2032-06-01 | 146.1% | 1.63%
| 2032-07-01 | 147.7% | 1.64%
| 2032-08-01 | 149.4% | 1.651%
| 2032-09-01 | 151% | 1.662%
| 2032-10-01 | 152.7% | 1.673%
| 2032-11-01 | 154.4% | 1.685%
| 2032-12-01 | 156.1% | 1.696%
| 2033-01-01 | 157.8% | 1.707%
| 2033-02-01 | 159.5% | 1.718%
| 2033-03-01 | 161.2% | 1.73%
| 2033-04-01 | 163% | 1.741%
| 2033-05-01 | 164.7% | 1.753%
| 2033-06-01 | 166.5% | 1.765%
| 2033-07-01 | 168.3% | 1.777%
| 2033-08-01 | 170% | 1.788%
| 2033-09-01 | 171.8% | 1.8%
| 2033-10-01 | 173.7% | 1.812%
| 2033-11-01 | 175.5% | 1.824%
| 2033-12-01 | 177.3% | 1.837%
| 2034-01-01 | 179.2% | 1.849%
| 2034-02-01 | 181% | 1.861%
| 2034-03-01 | 182.9% | 1.874%
| 2034-04-01 | 184.8% | 1.886%
| 2034-05-01 | 186.7% | 1.899%
| 2034-06-01 | 188.6% | 1.911%
| 2034-07-01 | 190.5% | 1.924%
| 2034-08-01 | 192.5% | 1.937%
| 2034-09-01 | 194.4% | 1.95%
| 2034-10-01 | 196.4% | 1.963%
| 2034-11-01 | 198.3% | 1.976%
| 2034-12-01 | 200.3% | 1.989%
| 2035-01-01 | 202.3% | 2.002%
| 2035-02-01 | 204.4% | 2.016%
| 2035-03-01 | 206.4% | 2.029%
| 2035-04-01 | 208.4% | 2.043%
| 2035-05-01 | 210.5% | 2.056%
| 2035-06-01 | 212.6% | 2.07%
| 2035-07-01 | 214.6% | 2.084%
| 2035-08-01 | 216.7% | 2.098%
| 2035-09-01 | 218.8% | 2.112%
| 2035-10-01 | 221% | 2.126%
| 2035-11-01 | 223.1% | 2.14%
| 2035-12-01 | 225.3% | 2.154%
| 2036-01-01 | 227.4% | 2.168%
| 2036-02-01 | 229.6% | 2.183%
| 2036-03-01 | 231.8% | 2.197%
| 2036-04-01 | 234% | 2.212%
| 2036-05-01 | 236.3% | 2.227%
| 2036-06-01 | 238.5% | 2.242%
| 2036-07-01 | 240.8% | 2.257%
| 2036-08-01 | 243% | 2.272%
| 2036-09-01 | 245.3% | 2.287%
| 2036-10-01 | 247.6% | 2.302%
| 2036-11-01 | 249.9% | 2.317%
| 2036-12-01 | 252.3% | 2.333%
| 2037-01-01 | 254.6% | 2.348%
| 2037-02-01 | 257% | 2.364%
| 2037-03-01 | 259.4% | 2.38%
| 2037-04-01 | 261.8% | 2.396%
| 2037-05-01 | 264.2% | 2.412%
| 2037-06-01 | 266.6% | 2.428%
| 2037-07-01 | 269% | 2.444%
| 2037-08-01 | 271.5% | 2.46%
| 2037-09-01 | 274% | 2.477%
| 2037-10-01 | 276.5% | 2.493%
| 2037-11-01 | 279% | 2.51%
| 2037-12-01 | 281.5% | 2.526%
| 2038-01-01 | 284% | 2.543%
| 2038-02-01 | 286.6% | 2.56%
| 2038-03-01 | 289.2% | 2.577%
| 2038-04-01 | 291.8% | 2.595%
| 2038-05-01 | 294.4% | 2.612%
| 2038-06-01 | 297% | 2.629%
| 2038-07-01 | 299.7% | 2.647%
| 2038-08-01 | 302.3% | 2.664%
| 2038-09-01 | 305% | 2.682%
| 2038-10-01 | 307.7% | 2.7%
| 2038-11-01 | 310.4% | 2.718%
| 2038-12-01 | 313.2% | 2.736%
| 2039-01-01 | 315.9% | 2.754%
| 2039-02-01 | 318.7% | 2.773%
| 2039-03-01 | 321.5% | 2.791%
| 2039-04-01 | 324.3% | 2.81%
| 2039-05-01 | 327.1% | 2.829%
| 2039-06-01 | 330% | 2.847%
| 2039-07-01 | 332.8% | 2.866%
| 2039-08-01 | 335.7% | 2.886%
| 2039-09-01 | 338.6% | 2.905%
| 2039-10-01 | 341.6% | 2.924%
| 2039-11-01 | 344.5% | 2.944%
| 2039-12-01 | 347.5% | 2.963%
| 2040-01-01 | 350.4% | 2.983%
| 2040-02-01 | 353.4% | 3.003%
| 2040-03-01 | 356.5% | 3.023%
| 2040-04-01 | 359.5% | 3.043%
| 2040-05-01 | 362.6% | 3.063%
| 2040-06-01 | 365.7% | 3.084%
| 2040-07-01 | 368.8% | 3.104%
| 2040-08-01 | 371.9% | 3.125%
| 2040-09-01 | 375% | 3.146%
| 2040-10-01 | 378.2% | 3.167%
| 2040-11-01 | 381.4% | 3.188%
| 2040-12-01 | 384.6% | 3.209%

## UWSA Escalation Calculation
2023-25 Capital Budget: Escalation Calculator
Unescalated Project Budget | 0 | ENR Index Value
Base Date | 2023-01-01 | 7976.68
Escalation Date | 2029-07-01 | 14068.0911
Escalation Factor | 1.7637
Escalation Amount | 0 | 0 | Delta UWSA Calculation vs. DFD Estimation
Escalated Project Budget | 0
Note on B3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This value will auto-complete based on PBW_NoInflationWorksheet.
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This value will auto-complete based on Project Budget Worksheet (PBW).
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This value will auto-complete based on Project Budget Worksheet (PBW).
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This value will auto-complete based on Project Budget Worksheet (PBW).
Note on C5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This value will auto-complete based on Project Budget Worksheet (PBW).
Note on B6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This value will auto-complete based on Project Budget Worksheet (PBW).
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This value will auto-complete based on Project Budget Worksheet (PBW).

## READ ME
CAPITAL PROJECT BUDGET WORKSHEETS Rev. 2023-03
Tab | WORKSHEET INDEX (left to right worksheets organized top to bottom below)
1 | Quick Inflation Factor Update: Maps content from PBW worksheet, intended for scenario planning w/o modifying PBW worksheet.
2 | Quick Inflation Date Update: Maps content from PBW worksheet, intended for scenario planning w/o modifying PBW worksheet.
3 | PBW_Summary: Summarizes and maps content from PBW worksheet.
4 | PBW: Project Budget Worksheet template and primary worksheet intended for user entry/modification.
5 | PBW_Summary_NoInflation: Summarizes and maps content from PBW_NoInflation worksheet.
6 | PBW_NoInflation: Maps content from PBW worksheet and changes Escalation Factor to 1.0000 to remove inflation.
7 | ENR: Engineering New Record's Building Cost Index History and Forecast based on anticipated inflation rates.
8 | DFD Inflation Estimation Tool: DFD's 2023-25 inflation estimate worksheet used to calculate amount of inflation in each request.
9 | DFD Inflation Summary: DFD's lookup worksheet for inflation calculations based on July 2022 Base Date and antcipated Bid Date.
10 | UWSA Escalation Calculation: Maps content from PBW_NoInflation and PBW worksheets.
11 | READ ME: Provides Worksheet Index and some narrative directions and references to template contents and intents.
12 | COST GUIDELINES: Unit construction cost ranges and reference for various building space types. Auto-inflates costs based on ENR.
13 | SAMPLE: Guide and Sample of the PBW Worksheet, intended to show completed template and formatting/nomenclature standards.
14 | LOOKUPS: Lookup values for PBW Revision Date and currentness, Project Type selections, and Duration by Project Size Matrix.
1 | This budget worksheet should be flexible enough for all capital project request types: Small Projects, All Agency Projects, Instructional Space Projects, Minor Projects, enumerated Major Projects, and UW Managed projects. All dark red text fields are unlocked and intended for user entry and definition. All other fields are locked and protected from user entry or modification.
2 | This worksheet allows renovation costs estimates to be conducted using a "Remodeling by Space Type" and/or "Remodeling by Trade" methodologies. Using both methodologies in a single budget estimate would be unusual and could lead to duplicative cost estimates. Use with caution. The "Remodeling by Trade" line items now include a Notes field for user text entry to clarify, further define, and/or re-define the standard category terms. The Notes field should be used when the standard unit costs are overwritten by the user. Cel H63 will automatically highlight in red if both "Remodeling by Space Type" and "Remodeling by Trade" section are used.
3 | Since most capital projects require feasibility and/or pre-design estimates, the budget worksheet has been modified to offer more flexibility in the arrangement and organization of the line items. Page 2 is now structured to allow the greatest flexibility to insert line items. Smart code identifiers (i.e. MasterFormat or UniFormat) can be entered; quantity/unit of measure/unit costs must be entered to calculate the line item cost; and the user determines the organization headings and can arrange the information to their specification. See Note #6 below for further information.
NOTE: If a 3rd party detailed budget estimate already exists in some other format, it is recommended those construction costs be entered as a lump sum item and the detailed budget estimate be referenced in the line item description vs. recreating the detail in this budget worksheet. If a 3rd party detailed budget estimate is not taken in whole as the basis for this budget estimate, the pertinent detail should be recreated here and be easily referenced and discoverable in the 3rd party estimate in terms of line item organization and terminology.
4 | The Base Date and Escalation Date cells can now use any combination of month and year (previous editions only allowed January or July) from January 2011 - December 2050. Consequently, the ENR Index lookup table has also been expanded to allow lookup of inflation values for any combination of Base Date and Escalation Date...this is most useful for future PBW template editions which will contain updated and actual/corrected ENR Index values vs. the projected estimates embedded in each edition of the template. There are three fields for ENR Escalation factors on Page 1. "Escalation (Calculated)" is a lookup of the inflation factor based on the Base Date and Escalation Date data entry values in this worksheet and the projections contained in the embedded ENR Index worksheet. "Escalation (Manual)" defaults to the "Escalation (Calculated)" value, but can be manually overwrtten by the user using a future PBW template with updated and corrected ENR values. Manual overrides below the default will highlight in red, above the default will highlight in yellow, and unchanged will highlight in green. "Escalation Delta (Manual - Calculated)" calculates the difference between the default value embedded in the ENR Index and the manual override. ENR Index values in BLACK TEXT are actual values, RED TEXT is projected/estimated based on the Annual Inflation Factor Estimate at the top of the worksheet.
5 | There are two new worksheets in the PBW template…Quick Inflation Date Update (QIDU) and Quick Inflation Factor Update (QIFU). Both are designed and intended to allow quick budget estimate updates without having to recreate the entire PBW detail. The Quick Inflation Date Update worksheet can be used to publish a current budget estimate without all the projected and estimated inflation, for example, at the time the A/E Design Team is hired. The inflation has to be earned rather than assumed as part of the base project budget. The Quick Inflation Factor Update worksheet can be used to re-estimate the entire project budget estimate using a corrected and actual ENR Index inflation factor value from a future PBW template edition (for example 12-18 months post original PBW creation).
6 | Movable and Special Equipment is handled with more flexibility and user control than previous PBW template editions. This type of budget information have now been retitled Furnishings, Fixtures, and Equipment to align with industry terminology standards. There are now three methods in which to enter this type of information: (1) on Page 2, at the bottom, under the section titled Contractor Furnished, Contractor Installed (CFCI). This section is integrated into the construction budget estimate and therefore has the full Design Fee and pertinent Additional Design Fees applied to it. (2) on Page 3, under Section 3 titled Additional Design Services, there is a subsection for Owner Furnished, Contractor Installed (OFCI) items. These are items that have an additional design fee applied to the summation of items listed here...either for selection and specification; or selection, specification, design/layout, and procurement assistance; or something in-between. (3) on Page 3, under Section 6 titled Furnishings, Fixtures, and Equipment, there is a subsection for Owner Furnished, Owner Installed (OFOI) items that have no design fees applied, but are using project funds to be procured and installed by the institution.
7 | At the bottom of the PBW_Summary worksheet is a table which can be selected, copied, and pasted directly into the Capital Project Request's Project Budget section. The table formatting is identical in cell and font size, style, and color.
8 | Architectural/Engineering Basic Design Fees Guidance: Current as per DFD's biennial capital budget instructions (2023-25). Outlined below for ease of reading since new Excel in-cell Comments do not allow formatted text.
New Construction Design Fee Guidance Project Complexity Construction Cost HIGH ¦ AVG ¦ LOW ≦ $100K: (14.2% ¦ 13.6% ¦ 12.8%) $100K - $500K: (14.1% ¦ 13.3% ¦ 12.3%) $500K - $1M: (11.6% ¦ 10.9% ¦ 9.9%) $1M - $2.5M: (10.6% ¦ 9.8% ¦ 8.8%) $2.5M - $5M: ( 9.2% ¦ 8.3% ¦ 7.3%) $5M - $30M: ( 8.3% ¦ 7.4% ¦ 6.3%) $30M - $50M: ( 7.0% ¦ 6.2% ¦ 5.3%) $50M+: ( 6.1% ¦ 5.5% ¦ 4.7%)
Renovation & Remodeling Design Fee Guidance Project Complexity Construction Cost HIGH ¦ AVG ¦ LOW ≦ $100K: (16.0% ¦ 14.0% ¦ 13.0%) $100K - $500K: (14.3% ¦ 13.5% ¦ 12.5%) $500K - $1M: (12.0% ¦ 11.1% ¦ 10.1%) $1M - $2.5M: (10.9% ¦ 9.9% ¦ 8.9%) $2.5M - $5M: ( 9.4% ¦ 8.5% ¦ 7.4%) $5M - $30M: ( 8.4% ¦ 7.5% ¦ 6.4%) $30M - $50M: ( 7.1% ¦ 6.3% ¦ 5.4%) $50M+: ( 6.2% ¦ 5.6% ¦ 4.8%)
If programming is not done by the agency, or if extensive program verification is required, an additional 0.1% to 1.5% should be added to the fee guidance shown above. High Complexity: Most complex projects both in design and detail include buildings of specialized architectural character, memorial, historic or monumental nature requiring special study or analysis and/or involve complex programs, mechanical systems, code requirements, etc. Project types include auditorium/theaters, communication buildings, extended care facilities, complex engineering projects, laboratories, historical restoration, and museums. Average Complexity: Project types include readiness centers, building systems, maintenance shops, firing ranges, recreational facilities, teaching laboratories, medical offices & clinics, laundry facilities, office buildings, site utilities, university centers, residence halls, and child day care facilities. Low Complexity: Projects are simple or repetitive construction without any great degree of special finish or design effort. May include projects where equipment purchase comprises a large portion of the construction budget. Project types include asbestos removal, building envelope repairs, roofing, life safety compliance, demolition, minimum security correctional centers, park shelters, warehouse, radio/television towers, service garage, and site work.
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Intended that the modified Inflation Factor entered here would be determined and calculated based on a later PBW Revision template with a more current and updated ENR worksheet content. The ENR worksheet content included in this file is frozen in time.
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Primarily intended to quickly see differences in budget estimates for proposed accelerated schedules.
Note on B6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Although it is possible to make duplicates of the PBW worksheet in the same file to explore alternatives and options, the PBW_Summary worksheet will only map to the original PBW worksheet content.
Note on B10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data source found at <https://www.enr.com/economics/historical_indices/building_cost_index_history>, but requires user account to access data content.
Note on B11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Modified by UWSA to extend possible Bid Date range as DFD’s standard template only allowed Bid Dates through June 2026.
Note on B13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Modeled after DFD’s Inflation Estimation Tool worksheet, but allows multiple Base Dates and extends range of possible Bid Dates.
Note on B17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PBW Revision Date and associated fields primarily created and generated to facilitate easy template updates without having to manually edit each worksheet in the template for a revision date.

## COST GUIDELINES
NEW CONSTRUCTION COST GUIDELINES Rev. 2023-03
SPACE CATEGORY | GSF | EFFICIENCY | $/GSF RANGE |  | COMMENTS and NOTES
|  |  | LOW END | HIGH END
Classrooms | 140000 | 65 | 251 | 332
Academic – Multi Use | 140000 | 65 | 251 | 276
Fine Arts Auditorium | 10000 | 65 | 497 | 773
Food Service | 30000 | 65 | 292 | 392 | Movable furnishings, kitchen appliances and fixtures, and specialty items (i.e. coolers or freezers sized for more than day use, blast freezers, large exhaust ventilation hoods) are not included in these $/GSF figures.
Laboratory Space
● Fine Arts Instructional Laboratory | 100000 | 62 | 332 | 387
● Instructional Dry Laboratory | 25000 | 60 | 362 | 392
● Instructional Wet Laboratory | 25000 | 58 | 492 | 713
● Research Laboratory | 100000 | 55 | 477 | 713
● Animal Space | 15000 | 55 | 633 | 693
● Computer Laboratory | 25000 | 65 | 297 | 392
● Instructional Greenhouse | 10000 | 80 | 297 | 332
● Research Greenhouse | 25000 | 80 | 332 | 382
Library | 80000 | 65 | 221 | 317
Offices
● 1 story | 10000 | 65 | 211 | 266 | For offices as part of other buildings with higher costs/ GSF use average of office cost and the other space type cost
● 2-4 stories | 40000 | 65 | 201 | 266
Physical Education | 120000 | 70 | 231 | 266
● Arena | 80000 | 78 | 231 | 276
● Field House | 45000 | 75 | 221 | 251
● Gymnasium/Track | 115000 | 74 | 166 | 196
● Pool | 10000 | 78 | 332 | 387
Residence Hall
● Semi-Suite Doubles (Type 2) | 160000 | 80 | 261 | 352
● Suite Style (Type 3) | 110000 | 80 | 261 | 352 | $63,000 - $75,000/ bed
Student Union | 100000 |  | 332 | 372
Agricultural
● Animal Housing | 35000 | 85 | 141 | 166 | Pole Barn, includes fixed equipment
● Hay Storage | 15000 | 90 | 111 | 141 | Pole Barn, unheated
Service and Maintenance | 25000 | 85 | 166 | 196
Storage (Prefabricated Metal)
● Unheated | 4000 | 95 | 86 | 116
● Heated | 4000 | 95 | 111 | 151
Parking | CAPACITY |  | $/STALL RANGE
● Freestanding ramp | 500 stalls | 55 | 17600 | 22700
● Ramp beneath building | 100 stalls | 52 | 32200 | 49700
● Surface Lot | 200 stalls |  | 4400 | 6900

## SAMPLE
THE UNIVERSITY OF WISCONSIN SYSTEM | [6 empty] | PROJECT BUDGET WORKSHEET GUIDE & SAMPLE Rev. 2023-03
PROJECT TITLE: | OLD MAIN MEMORIAL HALL ADDITION & RENOVATION - PHASE VIII |  |  |  | Date Prepared: |  | 2022-12-01
LOCATION: | UNIVERSITY OF WISCONSIN SYSTEM |  |  |  | Prepared By: |  | XXX
PROJECT TYPE: | MP | MAJOR PROJECT |  |  | Revised By: |  | XXX
OPTION NO.: | PRE-DESIGN COST ESTIMATE (23X8X, 04/01/2022) |  |  |  | TOTAL PROJECT COST ESTIMATE: |  | 218169000
NEW BUILDING AREA | [5 empty] | ENR Index # | Month/Year
ASF New Const | 16665 |  |  |  | Base Date: | 7971.96 | 2022-12-01
GSF New Const | 25100 | 66.39% | Efficiency |  | Bid Date: | 12482.2473 | 2028-01-01
[5 empty] | Escalation Factor (Calculated): |  | 1.5658
REMODELING AREA |  |  |  |  | Escalation Factor (Manual): |  | 1.5658
GSF Remodeling | 50800 |  |  |  | Escalation Delta (Manual - Calculated): |  | 0
GSF Total Bldg | 0 | 0% | Remodeling |  | Occupancy Date: | 42 months | 2031-07-01 12:00
NEW CONSTRUCTION BY SPACE TYPE
Space Category | ASF | Eff | GSF | $/GSF |  | Category Cost
Entrance/Lobby | 1111 | 0.75 | 1500 | 111 |  | 166500
Classrooms | 2222 | 0.6 | 3700 | 222 |  | 821400
Laboratories | 3333 | 0.52 | 6400 | 333 |  | 2131200
Offices | 4444 | 0.67 | 6600 | 444 |  | 2930400
Storage | 5555 | 0.8 | 6900 | 555 |  | 3829500
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
| 16665 |  | 25100 |  | Subtotal: $ | 9879000
NEW CONSTRUCTION COST SUBTOTAL | [6 empty] | 9879000
REMODELING BY SPACE TYPE
Space Category | ASF | Eff | GSF | $/GSF |  | Category Cost
Classrooms | 6666 | 0.6 | 11100 | 666 |  | 7392600
Laboratories | 7777 | 0.52 | 15000 | 777 |  | 11655000
Offices | 8888 | 0.67 | 13300 | 888 |  | 11810400
Multi-Purpose | 9999 | 0.88 | 11400 | 999 |  | 11388600
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
Function | 0 | 0 | 0 | 0 |  | 0
| 33330 |  | 50800 |  | Subtotal: $ | 42247000 | 42247000
REMODELING BY TRADE
Trade Category |  |  | GSF | $/GSF | DFDM $/GSF | Trade Cost
General | Notes
-Surface Treatment | Suspended acoustical ceiling panels only |  | 8888 | 2.29 | 16 | 20400
-Minor | X |  | 0 | 56 | 56 | 0
-Partial | X |  | 8888 | 92 | 92 | 817700
-Complete | X |  | 0 | 111 | 111 | 0
Plumbing
-Minor | X |  | 0 | 18 | 18 | 0
-Partial | Updated unit cost from contractor |  | 8888 | 29.29 | 31 | 260300
-Complete | X |  | 0 | 35 | 35 | 0
-Special Laboratory Needs | X |  | 0 | 66 | 66 | 0
Heat/Vent/Air Cond
-Minor | X |  | 0 | 24 | 24 | 0
-Partial | X |  | 0 | 51 | 51 | 0
-Complete | X |  | 88888 | 76 | 76 | 6755500
Electric
-Minor | X |  | 0 | 19 | 19 | 0
-Partial | X |  | 0 | 34 | 34 | 0
-Complete | X |  | 88888 | 43 | 43 | 3822200
[5 empty] | Subtotal: $ | 11676000
REMODELING COST SUBTOTAL (cell H63 will highlight red if Remodeling by Space Type and Remodeling by Trade sections are both used) | [5 empty] | ERROR? | 11676000
NEW CONSTRUCTION & REMODELING COST SUBTOTAL | [6 empty] | 63802000
PROJECT TITLE: | OLD MAIN MEMORIAL HALL ADDITION & RENOVATION - PHASE VIII
NEW CONSTRUCTION & REMODELING COST SUBTOTAL (from page 1) | [6 empty] | 63802000
ADDITIONAL CONSTRUCTION & REMODELING COSTS:
HEADING NAME OR ITEM CODE | ITEM DESCRIPTION |  |  | QUANTITY | UNIT | UNIT COST | SUBTOTAL
DEMO | DEMOLITION (RAZING GROSS SQUARE FOOTAGE) |  |  | 88888 | GSF | 19.8001 | 1760000
ADDITIONAL CONSTRUCTION & REMODELING COSTS
1. HEADING #1 | [6 empty] | 0
| HEADING #1, LINE ITEM #1 |  |  | 8 | EACH | 888 | 7100
| HEADING #1, LINE ITEM #2 |  |  | 88 | SF | 88 | 7700
| HEADING #1, LINE ITEM #3 |  |  | 888 | LF | 8 | 7100
2. HEADING #2 | [6 empty] | 0
| HEADING #2, LINE ITEM #1 |  |  | 8 | ASF | 8888 | 71100
| HEADING #2, LINE ITEM #2 |  |  | 88 | GSF | 888 | 78100
| HEADING #2, LINE ITEM #3 |  |  | 888 | VF | 88 | 78100
| HEADING #2, LINE ITEM #4 |  |  | 8888 | ACRES | 8 | 71100
3, HEADING #3 | [6 empty] | 0
| HEADING #3, LINE ITEM #1 |  |  | 8 | EACH | 8888 | 71100
| HEADING #3, LINE ITEM #2 |  |  | 88 | ASF | 888 | 78100
| HEADING #3, LINE ITEM #3 |  |  | 888 | GSF | 88 | 78100
| HEADING #3, LINE ITEM #4 |  |  | 8888 | LF | 8 | 71100
0
0
| …OR… | [5 empty] | 0
0
0
23X8X | PRE-DESIGN BUDGET ESTIMATE (04/01/2022, pp. 88-99) |  |  | 1 | LUMP SUM | 8888888 | 8888900
0
0
0
0
0
0
0
0
0
0
0
0
0
0
ADDITIONAL CONSTRUCTION & REMODELING COSTS: | [6 empty] | 9508000
FURNISHINGS, FIXTURES, & EQUIPMENT (FF&E): CONTRACTOR FURNISHED, CONTRACTOR INSTALLED (CFCI)
FURNISHINGS | TELESCOPING BLEACHERS |  |  | 1 | EACH | 888888 | 888900
TELECOMMUNICATIONS | RADIO TOWER |  |  | 1 | EACH | 88888 | 88900
EQUIPMENT | AUTOCLAVE |  |  | 1 | EACH | 8888 | 8900
ATHLETICS/RECREATION | CLIMBING WALL & ROPES COURSE |  |  | 1 | EACH | 888 | 900
0
0
0
0
FF&E: CFCI | [6 empty] | 988000
ADDITIONAL CONSTRUCTION & REMODELING COST SUBTOTAL | [6 empty] | 12256000
CONSTRUCTION & REMODELING COST SUBTOTAL | [6 empty] | 76058000
HAZ MATS | HAZARDOUS MATERIALS ABATEMENT |  |  | 88888 | SF | 8 | 711000
PROJECT TITLE: | OLD MAIN MEMORIAL HALL ADDITION & RENOVATION - PHASE VIII
CONSTRUCTION & REMODELING COST SUBTOTAL (from page 2) | [6 empty] | 76058000
1. Total Construction Cost | [6 empty] | 151959000
NEW CONSTRUCTION & REMODELING COST (from Page 1) |  |  |  | 63802000
DEMOLITION (from Page 2) |  |  |  | 1760000
ADDITIONAL CONSTRUCTION & REMODELING COST (from Page 2) |  |  |  | 9508000
FF&E: CFCI (from Page 2) |  |  |  | 988000
CONSTRUCTION & REMODELING COST SUBTOTAL (from Page 2) |  |  |  | 76058000
Design Contingency |  | 8.889% | 76058000 | 6760600
General Conditions |  | 8.889% | 76058000 | 6760600
Overhead & Profit (OH&P) |  | 8.889% | 76058000 | 6760600
HAZARDOUS MATERIALS ABATEMENT (from Page 2) |  |  |  | 711000
Unescalated Construction Cost Subtotal |  |  |  | 97050800
Escalation Factor (from Page 1) |  | 1.5658 | 97050800 | 151959100
2. Architect/Engineer Basic Services | [5 empty] | 9.245% | 14048000
- Basic Services (Calculated % of Construction $) |  | 8.889% | 151959000 | 13507300
- Basic Services (Enter Direct $ for Basic A/E Fees) |  |  |  | 0
- Reimbursible costs |  | 4% | 13507300 | 540300
3. Additional Design Services | [5 empty] | 2.147% | 3262000
- Pre-design |  | 1% | 151959000 | 1519600
- LEED™ certification |  |  |  | 0
- Commissioning (Level 1 or 2) |  | 1% | 151959000 | 1519600
- EIS/EIA consultant |  |  |  | 0
- Construction Testing |  |  |  | 0
- Testing & Balancing |  |  |  | 0
- Hazardous Materials Design |  |  |  | 8888
- Geotechnical Survey |  |  |  | 88888
- DSPS Plan Review |  |  |  | 8888
- Specify Additional Design Service |  |  |  | 0
- Furnishings, Fixtures, & Equipment (FF&E) Design Fee |  | 10% | 1164400 | 116400
Furnishings, Fixtures, & Equipment (FF&E): Owner Furnished, Contractor Installed (OFCI) |  |  |  |  | FF&E: OFCI | 1164400
- Audio-Visual and Computer Equipment |  |  |  | 888888
- Systems Furniture |  |  |  | 88888
- Laboratory Casework/Workstations (Mobile) |  |  |  | 8888
- Information/Library Kiosks (Mobile) |  |  |  | 88888
- Dining Booths |  |  |  | 88888
4. Project Contingency |  | 15% | 151959000 | 22793900 |  |  | 22794000
5. Project Management |  | 4% | 174753000 | 6990100 |  |  | 6990000
6. Furnishings, Fixtures, & Equipment (FF&E) | [5 empty] | 12.58% | 19116000
- FF&E: OFCI (from #3 above) |  |  |  | 1164400
Furnishings, Fixtures, & Equipment (FF&E): Owner Furnished, Owner Installed (OFOI) |  |  |  |  | FF&E: OFOI | 17951700
- Movable & Special Equipment Allowance (% of Construction $) |  | 8.889% | 151959000 | 13507300
- Audio-Visual and Computer Equipment |  |  |  | 888888
- Systems Furniture |  |  |  | 888888
- Waste Management/Recycling Equipment |  |  |  | 888888
- Loading dock Equipment |  |  |  | 888888
- Bike Racks, Site Furnshings, and Flag Poles |  |  |  | 888888
TOTAL PROJECT BUDGET ESTIMATE | [6 empty] | 218169000
|  | 1127 | /ASF: Construction Cost (building & site)
|  | 1002 | /GSF: Construction Cost (building & site)
|  | 3234 | /ASF: Total Project Cost
|  | 2874 | /GSF: Total Project Cost
NOTES:
X
X
X
X
X

## LOOKUPS
Rev. 2023-03 |  | PROJECT TYPE |  | DURATION
2023-03-01 |  | AA | ALL AGENCY | 5000 | 300000 | 182.5
2023-03-01 16:54 | NOW | IS | INSTRUCTIONAL SPACE | 300000 | 3000000 | 365
2021-03-01 16:54 | NOW-730 | MFR | MINOR FACILITIES RENEWAL | 3000000 | 7400000 | 547.5
2019-03-02 16:54 | NOW-1460 | MP | MAJOR PROJECT | 7400000 | 15000000 | 912.5
|  | P&D | PLANNING & DESIGN | 15000000 | 30000000 | 1095
|  | SP | SMALL PROJECT | 30000000 | 1000000000 | 1277.5
|  | X | UNSPECIFIED